ENGR-KB

Engineering Knowledge Base

Cost Estimating

Equations, Models, Data Structures & GeoLab Integration

v1.0  |  February 2026

ENGR-KB Document Series  |  Document 2 of 6

DRAFT — INTERNAL USE ONLY

# Table of Contents

# 1. Cost Estimating Domain Overview

The Cost Estimating domain provides a comprehensive, deterministic calculation engine for construction cost estimation across the full project lifecycle—from Class 5 screening estimates through Class 1 definitive estimates. The engine handles unit cost management, assembly composition, cost escalation, location adjustment, parametric modeling, contingency analysis, and earthwork quantity/cost integration with GeoLab.

Core Design Principle: Every cost estimate carries explicit metadata about its basis, confidence level, and limitations. The system never presents a rough estimate with false precision. Ranges, contingencies, and confidence levels are first-class citizens in every data model and output.

## 1.1 Scope of Coverage

The cost estimating engine covers the following work categories, organized by CSI MasterFormat divisions most relevant to geotechnical and heavy civil construction:

| CSI Division | Title | Coverage Depth | GeoLab Integration |
| --- | --- | --- | --- |
| 01 | General Requirements | Moderate | Testing/inspection costs |
| 02 | Existing Conditions | Deep | Subsurface investigation, hazmat, demo |
| 03 | Concrete | Deep | Foundations, walls, slabs, structural |
| 05 | Metals | Moderate | Structural steel, misc. metals |
| 31 | Earthwork | Comprehensive | Primary GeoLab bridge domain |
| 32 | Exterior Improvements | Deep | Paving, curb, sidewalk, grading |
| 33 | Utilities | Deep | Water, sewer, storm, electrical duct banks |
| 35 | Waterway & Marine | Moderate | Dams, levees, channels |
| 41 | Material Processing | Light | Crushing, screening, batch plants |

## 1.2 Estimate Types Supported

| Estimate Type | AACE Class | Input Required | Output |
| --- | --- | --- | --- |
| Screening / Order of Magnitude | 5 | Project type, capacity/size parameter | Cost range (±50%) |
| Feasibility / Concept | 4 | Preliminary design, site conditions | Cost range (±30%) |
| Budget Authorization | 3 | Semi-detailed design, quantities | Budget estimate (±20%) |
| Control / Bid Preparation | 2 | Detailed design, takeoff quantities | Detailed estimate (±15%) |
| Definitive / Check Estimate | 1 | Complete design, detailed takeoff | Definitive estimate (±10%) |

## 1.3 What This Engine Is NOT

To set appropriate expectations and avoid misuse:

- Not a replacement for professional estimators. The engine provides calculations, data, and structure. Engineering judgment on scope, means/methods, and risk remains a human responsibility.

- Not a proprietary cost database. Ships with public reference ranges, not RSMeans or equivalent commercial data. Users should calibrate with their own historical data or integrate commercial sources via API.

- Not a quantity takeoff tool. Quantities are inputs, not computed from drawings. Future phases may add AI-assisted takeoff from PDFs/CAD, but Phase 1 assumes quantities are provided.

- Not a bid preparation system. Does not handle bid strategy, bid bond calculations, or competitive analysis. It produces cost estimates that inform bids.

# 2. AACE Estimate Classification System

All estimates in ENGR-KB carry mandatory AACE classification metadata per AACE International Recommended Practice 18R-97 (updated). This classification drives every downstream behavior: which calculation methods are available, what accuracy ranges are displayed, what contingency methods are appropriate, and how the workflow agent validates results.

## 2.1 Classification Matrix

The classification system maps project maturity (% design completion) to estimate accuracy. The engine enforces these boundaries—a user cannot assign Class 1 accuracy to an estimate based on conceptual-level inputs.

| Attribute | Class 5 | Class 4 | Class 3 | Class 2 | Class 1 |
| --- | --- | --- | --- | --- | --- |
| Project Definition Level | 0–2% | 1–15% | 10–40% | 30–75% | 65–100% |
| Typical Purpose | Screening | Feasibility | Budget auth. | Control/bid | Check/final |
| Low Range Accuracy | -20% to -50% | -15% to -30% | -10% to -20% | -5% to -15% | -3% to -10% |
| High Range Accuracy | +30% to +100% | +20% to +50% | +10% to +30% | +5% to +20% | +3% to +15% |
| Typical Contingency | 30–50% | 20–35% | 10–25% | 5–15% | 3–10% |
| Methodology | Parametric, analogous | Parametric, factored | Semi-detailed | Detailed unit cost | Detailed takeoff |
| Effort (% of project cost) | 0.005–0.015% | 0.01–0.03% | 0.02–0.10% | 0.05–0.15% | 0.10–0.25% |
| Preparation Time | Hours to days | Days to weeks | Weeks | Weeks to months | Months |

## 2.2 Classification Enforcement Logic

The engine validates that estimate inputs are consistent with the declared AACE class. This prevents common errors like applying parametric methods but claiming Class 2 accuracy.

class EstimateClassification(BaseModel):

aace_class: Literal[1, 2, 3, 4, 5]

project_definition_pct: float  # 0.0 to 1.0

methodology: EstimateMethodology

basis_documents: List[str]

accuracy_low: float            # negative %, e.g., -0.20

accuracy_high: float           # positive %, e.g., +0.30

contingency_pct: float

estimate_date: date

estimator: str

reviewer: Optional[str]

@model_validator(mode='after')

def validate_class_consistency(self):

rules = AACE_CLASS_RULES[self.aace_class]

if self.project_definition_pct < rules.min_definition:

raise ValueError(

f'Class {self.aace_class} requires >= '

f'{rules.min_definition*100}% project definition'

)

if self.methodology not in rules.allowed_methods:

raise ValueError(

f'{self.methodology} not permitted for Class {self.aace_class}'

)

return self

## 2.3 Methodology Constraints by Class

| Methodology | Description | Class 5 | Class 4 | Class 3 | Class 2 | Class 1 |
| --- | --- | --- | --- | --- | --- | --- |
| Analogous | Scale from similar completed project | ✓ | ✓ | — | — | — |
| Parametric | Statistical relationship (C = aX^b) | ✓ | ✓ | ✓ | — | — |
| Factored | Apply factors to known base cost | ✓ | ✓ | ✓ | — | — |
| Assembly-Based | Pre-built assemblies with unit costs | — | ✓ | ✓ | ✓ | — |
| Semi-Detailed | Approximate quantities × unit costs | — | — | ✓ | ✓ | ✓ |
| Detailed Takeoff | Exact quantities from drawings | — | — | — | ✓ | ✓ |

## 2.4 Estimate Maturation Tracking

As a project progresses through design phases, estimates mature from Class 5 toward Class 1. The system tracks this progression and maintains the full history for trend analysis and variance tracking.

class EstimateHistory(BaseModel):

project_id: str

estimates: List[EstimateVersion]

class EstimateVersion(BaseModel):

version: int

aace_class: int

date: date

total_cost: Decimal

accuracy_range: Tuple[float, float]

contingency_pct: float

change_drivers: List[ChangeDriver]

class ChangeDriver(BaseModel):

category: Literal['scope', 'market', 'design', 'risk', 'schedule', 'other']

description: str

cost_impact: Decimal

pct_impact: float

NOTE: The estimate history enables the agent to detect patterns like persistent cost growth, scope creep, or market-driven escalation. When a new estimate version shows >10% growth from the previous version, the agent flags it for management review with root cause analysis.

# 3. Cost Data Architecture

Cost data in ENGR-KB is organized in a four-tier hierarchy: raw unit costs at the bottom, composed into assemblies, aggregated into work packages, and rolled up into complete estimates. Every tier carries temporal (when), geographic (where), and confidence (how sure) metadata.

## 3.1 Unit Cost Model

The unit cost is the atomic element of the cost estimating system. Each unit cost represents the cost to perform one unit of a specific work item (e.g., one cubic yard of excavation, one linear foot of pipe).

class UnitCost(BaseModel):

# Identification

code: str                      # CSI work result code

description: str               # Human-readable description

unit: CostUnit                 # CY, SF, LF, TON, EA, HR, LS

# Cost Breakdown (all per unit)

material_cost: Decimal         # Material/supply cost per unit

labor_cost: Decimal            # Bare labor cost per unit

equipment_cost: Decimal        # Equipment operating cost per unit

subcontractor_cost: Decimal = Decimal('0')

# Production Data

labor_hours: Decimal           # Crew-hours per unit

crew_composition: CrewComposition

daily_output: Decimal          # Units per 8-hr crew-day

production_basis: str          # Assumed conditions description

# Cost Basis Metadata

base_date: date                # When this cost was valid

base_region: str               # Geographic basis (city/state)

cost_index_base: Decimal       # ENR CCI at base_date

source: CostSource             # Provenance tracking

confidence: float              # 0.0-1.0

# Adjustment Factors

waste_factor: Decimal = Decimal('1.0')

difficulty_factor: Decimal = Decimal('1.0')

# Validity Constraints

valid_quantity_range: Optional[Tuple[Decimal, Decimal]]

superseded_by: Optional[str]

notes: Optional[str]

@computed_field

@property

def total_unit_cost(self) -> Decimal:

return (self.material_cost + self.labor_cost +

self.equipment_cost + self.subcontractor_cost)

@computed_field

@property

def total_with_waste(self) -> Decimal:

return self.total_unit_cost * self.waste_factor

### 3.1.1 Crew Composition Model

Crew composition is modeled explicitly because labor cost varies dramatically by crew makeup, and the crew drives both cost and production rate.

class CrewComposition(BaseModel):

crew_code: str                 # e.g., 'B-12'

description: str               # 'Excavation crew, medium'

laborers: List[CrewMember]

equipment: List[CrewEquipment]

@computed_field

@property

def hourly_labor_cost(self) -> Decimal:

return sum(m.hourly_rate * m.count for m in self.laborers)

@computed_field

@property

def hourly_equipment_cost(self) -> Decimal:

return sum(e.hourly_rate * e.count for e in self.equipment)

@computed_field

@property

def daily_crew_cost(self) -> Decimal:

return (self.hourly_labor_cost + self.hourly_equipment_cost) * 8

class CrewMember(BaseModel):

role: str                      # 'Equipment Operator'

trade: str                     # 'Operating Engineer'

count: Decimal                 # Can be fractional (0.5 = half-time)

hourly_rate: Decimal           # Bare wage (no burden)

burden_rate: Decimal           # Fully burdened rate

class CrewEquipment(BaseModel):

equipment_type: str            # 'Excavator, 1.5 CY'

equipment_code: str            # Cross-ref to equipment library

count: int

hourly_rate: Decimal           # Owning + operating cost/hr

### 3.1.2 Cost Source Tracking

Every cost carries provenance data. This is critical for auditability and for the agent to assess reliability.

class CostSource(BaseModel):

source_type: Literal[

'published_reference',

'public_bid_tab',

'historical_project',

'vendor_quote',

'calculated',

'parametric',

'professional_judgment',

]

source_name: str

source_date: date

source_reference: Optional[str]

reliability_score: float      # 0.0-1.0

sample_size: Optional[int]

IMPORTANT: Reliability scores: published references 0.7-0.9, bid tabs 0.8-0.95, historical projects 0.85-0.95, vendor quotes 0.90-0.98, professional judgment 0.3-0.7. The agent uses this to weight cost data when multiple sources exist for the same work item.

## 3.2 Assembly Model

Assemblies combine multiple unit costs into logical construction activities. This mirrors how construction work is actually performed—a concrete foundation wall includes formwork, rebar, embeds, concrete, finishing, stripping, and curing, each with its own unit cost and production rate.

class Assembly(BaseModel):

code: str                       # 'ASM-FND-001'

description: str

category: str                   # CSI Level 2 grouping

assembly_unit: CostUnit         # SF, LF, CY, EA

components: List[AssemblyComponent]

# Assembly-Level Factors

productivity_factor: Decimal = Decimal('1.0')

waste_factor: Decimal = Decimal('1.0')

complexity_factor: Decimal = Decimal('1.0')

# Documentation

base_date: date

assumptions: List[str]

exclusions: List[str]

applicable_specs: List[str]     # Spec section cross-refs

@computed_field

@property

def total_cost_per_unit(self) -> Decimal:

base = sum(c.extended_total for c in self.components)

return base * self.productivity_factor * self.waste_factor

class AssemblyComponent(BaseModel):

unit_cost_code: str

description: str

quantity_per_unit: Decimal       # Qty per assembly unit

component_unit: CostUnit

unit_cost_ref: Optional[UnitCost]  # Resolved at runtime

@computed_field

@property

def extended_total(self) -> Decimal:

if not self.unit_cost_ref: return Decimal('0')

return self.quantity_per_unit * self.unit_cost_ref.total_unit_cost

### 3.2.1 Worked Example: CIP Concrete Foundation Wall Assembly

Illustrates assembly composition for a 12-inch thick cast-in-place concrete foundation wall, measured per square foot of contact area (SFCA):

| Component | Unit | Qty/SFCA | Material | Labor | Equip | Total/SFCA |
| --- | --- | --- | --- | --- | --- | --- |
| Formwork (steel panel, 4 uses) | SFCA | 2.00 | $1.85 | $3.20 | $0.45 | $5.50 |
| Rebar (#5 @ 12" EW, 2.0 psf) | LB | 2.00 | $0.68 | $0.54 | $0.04 | $1.26 |
| Concrete (4000 psi, pump) | CF | 1.00 | $5.25 | $1.80 | $0.95 | $8.00 |
| Form ties and accessories | EA | 0.25 | $0.45 | $0.30 | — | $0.75 |
| Cure and protect | SFCA | 1.00 | $0.12 | $0.25 | — | $0.37 |
| Form stripping | SFCA | 1.00 | — | $0.65 | $0.10 | $0.75 |
| Assembly Total |  |  | $8.35 | $6.74 | $1.54 | $16.63 |

Notes: Illustrative reference values, Denver metro, Q1 2025 basis. Concrete qty of 1.00 CF/SFCA reflects 12" wall thickness. Rebar at 2.0 psf typical for this wall type. Steel panel forms with 4 reuses; plywood forms approximately 20% less material but 15% more labor.

## 3.3 Work Package & Estimate Models

Work packages group related line items into manageable chunks corresponding to schedule activities and cost accounts.

class WorkPackage(BaseModel):

code: str                       # WBS code, e.g., '31.1.1'

description: str

wbs_level: int

parent_code: Optional[str]

line_items: List[LineItem]

schedule_activity_id: Optional[str]

spec_sections: List[str]

@computed_field

@property

def direct_cost(self) -> Decimal:

return sum(li.extended_cost for li in self.line_items)

class LineItem(BaseModel):

line_number: int

description: str

quantity: Decimal

unit: CostUnit

unit_cost_code: Optional[str]

assembly_code: Optional[str]

unit_price: Decimal

extended_cost: Decimal

cost_type: Literal['material','labor','equipment','subcontract','lump_sum']

### 3.3.1 Complete Estimate Structure

class Estimate(BaseModel):

estimate_id: str

project_id: str

project_name: str

classification: EstimateClassification

version: int

# Cost Structure

work_packages: List[WorkPackage]

indirect_costs: IndirectCosts

contingency: ContingencyAllocation

escalation: EscalationAdjustment

markup: MarkupStructure

@computed_field

@property

def total_direct_cost(self) -> Decimal:

return sum(wp.direct_cost for wp in self.work_packages)

@computed_field

@property

def total_project_cost(self) -> Decimal:

subtotal = self.total_direct_cost + self.indirect_costs.total

with_contingency = subtotal + self.contingency.calculate(subtotal)

escalated = self.escalation.apply(with_contingency)

return self.markup.apply(escalated)

## 3.4 Indirect Costs Structure

Indirect costs are project-level costs not directly attributable to specific work items.

| Indirect Cost Category | Typical Range | Basis | Calculation Method |
| --- | --- | --- | --- |
| Mobilization/Demobilization | 3–8% | Fleet size, distance | Detailed or % of direct |
| General Conditions | 8–15% | Duration, complexity | Duration-based or % |
| Bonds (Perf. + Payment) | 0.5–2.5% | Contract value, rating | Published bond rates |
| Insurance (Builder’s Risk) | 0.5–1.5% | Project type, location | Quoted or standard |
| Permits and Fees | 0.5–3% | Jurisdiction | Actual or parametric |
| Engineering During Const. | 2–5% | Complexity | Effort estimate |
| Construction Management | 5–10% | Oversight requirements | Staff × duration |
| QC/Testing | 1–3% | Spec requirements | Spec-driven (from Specs KB) |
| Temporary Facilities | 1–4% | Duration, remoteness | Duration-based |
| Environmental Compliance | 1–4% | Permit conditions | Actual or parametric |

IMPORTANT: QC/Testing costs are a key integration point with the Specifications domain. When a spec requires testing at a defined frequency (e.g., 1 compaction test per 500 CY), the system auto-generates the testing cost based on earthwork volume. This is deterministic, not estimated.

## 3.5 Cost Unit Registry

All cost data uses standardized units from a controlled registry to prevent unit mismatch errors.

| Unit | Description | Category | Key Conversions |
| --- | --- | --- | --- |
| CY | Cubic Yard | Volume | 1 CY = 27 CF = 0.7646 m³ |
| BCY | Bank Cubic Yard | Volume (in-place) | BCY × swell = LCY |
| LCY | Loose Cubic Yard | Volume (hauled) | LCY × shrink = CCY |
| CCY | Compacted Cubic Yard | Volume (placed) | Target placement volume |
| SF | Square Foot | Area | 1 SF = 0.0929 m² |
| SFCA | Sq Ft Contact Area | Area (formwork) | Form face area |
| LF | Linear Foot | Length | 1 LF = 0.3048 m |
| TON | Short Ton (2000 lb) | Weight | 1 ton = 0.9072 metric ton |
| EA | Each | Count | — |
| HR | Hour | Time | 8 HR = 1 crew-day |
| LS | Lump Sum | Fixed | — |
| GAL | Gallon | Volume (liquid) | 1 GAL = 3.785 L |

WARNING: The BCY/LCY/CCY distinction is critical for earthwork. A common costly error: estimating excavation in bank measure but pricing hauling in bank measure—hauling should be loose measure (20-40% more volume). The system enforces volume state tracking.

# 4. Escalation & Location Adjustment

Construction costs vary significantly across time and geography. The escalation engine adjusts costs from their base date/location to any target date/location using published indices. All adjustments are deterministic—the system applies mathematical index ratios, not AI-estimated trends.

## 4.1 Time Escalation

### 4.1.1 Basic Time Escalation

CE-ESC-001: Single-Index Time Escalation

Adjusted Cost = Base Cost × (Index_target / Index_base)

| Variable | Description | Source |
| --- | --- | --- |
| Base Cost | Known cost at base_date | Unit cost, assembly, or bid price |
| Index_target | Construction cost index at target date | ENR CCI, BCI, or component index |
| Index_base | Construction cost index at base_date | Same index series as target |

NOTE: Always use the same index series for numerator and denominator. Mixing ENR CCI with BLS PPI produces meaningless results. The system enforces index series consistency at the model level.

### 4.1.2 Component-Level Escalation

CE-ESC-002: Weighted Component Escalation

Escalated = (Mat × Mat_Index_Ratio) + (Lab × Lab_Index_Ratio) + (Equip × Equip_Index_Ratio)

| Component | Recommended Index | Source | Volatility |
| --- | --- | --- | --- |
| Materials (aggregate) | BLS PPI for construction materials | Bureau of Labor Statistics | High |
| Materials (steel) | BLS PPI for steel mill products | Bureau of Labor Statistics | Very High |
| Materials (concrete) | BLS PPI for ready-mix concrete | Bureau of Labor Statistics | Moderate |
| Materials (lumber) | BLS PPI for lumber & wood products | Bureau of Labor Statistics | Very High |
| Materials (fuel) | EIA diesel fuel price index | Energy Information Admin. | Very High |
| Labor | BLS ECI, construction | Bureau of Labor Statistics | Low-Moderate |
| Equipment (ownership) | ENR Equipment Cost component | Engineering News-Record | Moderate |
| Equipment (operating) | EIA diesel + BLS maintenance PPI | Combined | High |

### 4.1.3 Midpoint and Cash-Flow Escalation

CE-ESC-003: Construction Midpoint Escalation

For multi-year projects, costs are escalated to the midpoint of construction, not the start date:

Midpoint Date = Start + (Duration / 2)

Escalated Cost = Base Cost × (Index_midpoint / Index_base)

CE-ESC-004: Cash-Flow-Weighted Escalation (projects >3 years)

Escalated Cost = Σ_i (Monthly_Spend_i × Index_month_i / Index_base)

This method uses the cost-loaded schedule to weight escalation by when money is actually spent. For front-loaded projects (heavy mobilization), this produces lower escalation than midpoint; for back-loaded projects (heavy finishing), it produces higher.

## 4.2 Geographic Location Adjustment

### 4.2.1 Basic Location Adjustment

CE-LOC-001: Single-Factor Location Adjustment

Adjusted Cost = Base Cost × (Target Factor / Base Factor)

Location factors are expressed relative to a national average (1.00). A city with factor 1.12 is 12% above national average.

### 4.2.2 Representative City Cost Indices

Representative total construction cost indices relative to national average (1.00). These are publicly available reference ranges—calibrate with current data.

| City | Material | Labor | Equipment | Total |
| --- | --- | --- | --- | --- |
| National Average | 1.00 | 1.00 | 1.00 | 1.00 |
| New York, NY | 1.12 | 1.45 | 1.05 | 1.22 |
| San Francisco, CA | 1.10 | 1.40 | 1.05 | 1.20 |
| Chicago, IL | 1.04 | 1.30 | 1.02 | 1.14 |
| Boston, MA | 1.08 | 1.32 | 1.03 | 1.16 |
| Seattle, WA | 1.06 | 1.22 | 1.02 | 1.11 |
| Denver, CO | 1.02 | 1.05 | 1.00 | 1.03 |
| Houston, TX | 0.98 | 0.92 | 0.98 | 0.95 |
| Atlanta, GA | 0.97 | 0.88 | 0.98 | 0.93 |
| Phoenix, AZ | 0.99 | 0.90 | 0.99 | 0.95 |
| Dallas, TX | 0.97 | 0.88 | 0.98 | 0.93 |
| Rural Midwest | 1.02 | 0.75 | 0.95 | 0.88 |
| Rural Mountain West | 1.05 | 0.80 | 0.98 | 0.92 |
| Alaska (urban) | 1.25 | 1.50 | 1.20 | 1.35 |
| Hawaii | 1.30 | 1.35 | 1.15 | 1.28 |

IMPORTANT: These are approximate reference values. Actual factors vary by work type and market. RSMeans publishes indices for 970+ locations annually. Users with RSMeans licenses should import via API.

### 4.2.3 Component-Level Location

CE-LOC-002: Weighted Component Location Adjustment

Adjusted = (Mat × Mat_Loc) + (Lab × Lab_Loc) + (Equip × Equip_Loc)

This matters because labor cost variation between locations is 3-5x larger than material or equipment variation. A 60% labor-driven job sees much larger location adjustments than a materials-heavy job.

## 4.3 Combined Adjustment

CE-COMB-001: Combined Time + Location

Final Cost = Base Cost × (Index_target / Index_base) × (Loc_target / Loc_base)

NOTE: Order of operations: Escalate first (time), then adjust for location. Escalation indices are published at a national geographic basis; location factors are published at a specific time basis (current year).

## 4.4 Escalation Data Model

class EscalationAdjustment(BaseModel):

base_date: date

target_date: date

base_location: str

target_location: str

method: Literal['simple', 'component', 'cash_flow']

time_indices: TimeIndexSet

location_factors: LocationFactorSet

combined_factor: Decimal

def apply(self, base_cost: Decimal) -> Decimal:

return base_cost * self.combined_factor

class TimeIndexSet(BaseModel):

index_series: str

base_value: Decimal

target_value: Decimal

material_base: Optional[Decimal]

material_target: Optional[Decimal]

labor_base: Optional[Decimal]

labor_target: Optional[Decimal]

equipment_base: Optional[Decimal]

equipment_target: Optional[Decimal]

class LocationFactorSet(BaseModel):

factor_source: str

base_total: Decimal

target_total: Decimal

base_material: Optional[Decimal]

target_material: Optional[Decimal]

base_labor: Optional[Decimal]

target_labor: Optional[Decimal]

## 4.5 Historical ENR Cost Index Data

The system ships with historical ENR Construction Cost Index data, the most widely used U.S. construction cost index:

| Year | ENR CCI | ENR BCI | Annual Change | Cumul. from 2015 |
| --- | --- | --- | --- | --- |
| 2015 | 10,137 | 5,486 | — | 1.000 |
| 2016 | 10,333 | 5,557 | +1.9% | 1.019 |
| 2017 | 10,751 | 5,771 | +4.0% | 1.061 |
| 2018 | 11,161 | 5,983 | +3.8% | 1.101 |
| 2019 | 11,379 | 6,114 | +2.0% | 1.123 |
| 2020 | 11,624 | 6,211 | +2.2% | 1.147 |
| 2021 | 12,565 | 6,620 | +8.1% | 1.240 |
| 2022 | 13,569 | 7,107 | +8.0% | 1.339 |
| 2023 | 13,908 | 7,310 | +2.5% | 1.372 |
| 2024 | 14,258 | 7,498 | +2.5% | 1.407 |
| 2025 (est.) | 14,615 | 7,690 | +2.5% | 1.442 |

WARNING: 2021-2022 shows exceptional 8%+ annual escalation from post-COVID disruptions. Pre-2020 historical data requires 15-20% compound escalation through this period. The agent flags estimates based on pre-2020 data for escalation review.

# 5. Parametric Estimating Models

Parametric estimating uses statistical relationships between project characteristics (size, capacity, output) and cost. These models are appropriate for Class 4-5 estimates where detailed design is unavailable. The general form is a power-law relationship, well-established in engineering economics.

## 5.1 General Parametric Form

CE-PAR-001: Power-Law Cost-Capacity Relationship

C = C_ref × (Q / Q_ref)^n × F_location × F_escalation × F_complexity

| Variable | Description | Typical Range |
| --- | --- | --- |
| C | Estimated cost of proposed facility | Output |
| C_ref | Known cost of reference facility | Historical or published |
| Q | Capacity/size of proposed facility | Design parameter |
| Q_ref | Capacity/size of reference facility | Historical record |
| n | Cost-capacity exponent (scaling factor) | 0.4 to 0.9 |
| F_location | Location adjustment factor | 0.85 to 1.35 |
| F_escalation | Time escalation factor | Calculated from indices |
| F_complexity | Complexity/difficulty factor | 0.8 to 1.5 |

The Six-Tenths Rule: When no specific data exists, n = 0.6 is the classic default for process/industrial facilities. However, exponents vary significantly by facility type. Using 0.6 blindly is a common and significant error.

## 5.2 Parametric Coefficients by Facility Type

### 5.2.1 Dams and Embankments

| Facility | Size Param | Exponent | R² | Source | Valid Range |
| --- | --- | --- | --- | --- | --- |
| Earthfill dam | Fill vol (MCY) | 0.60–0.70 | 0.85–0.92 | USBR hist. | 0.1–100 MCY |
| Rockfill dam | Fill vol (MCY) | 0.55–0.65 | 0.82–0.90 | USBR hist. | 0.5–200 MCY |
| Concrete gravity | Conc vol (MCY) | 0.65–0.75 | 0.80–0.88 | USACE hist. | 0.01–10 MCY |
| RCC dam | RCC vol (MCY) | 0.60–0.70 | 0.83–0.90 | USACE/USBR | 0.05–20 MCY |
| Levee/embankment | Length (miles) | 0.85–0.95 | 0.88–0.94 | USACE CW | 1–100 miles |
| Spillway (concrete) | Flow (CFS) | 0.55–0.65 | 0.78–0.86 | USBR/USACE | 100–500K CFS |
| Outlet works | Conduit dia (ft) | 0.70–0.80 | 0.75–0.85 | USBR hist. | 2–20 ft |

### 5.2.2 Water/Wastewater Facilities

| Facility | Size Param | Exponent | R² | Source | Valid Range |
| --- | --- | --- | --- | --- | --- |
| Water treatment | Capacity (MGD) | 0.65–0.75 | 0.90–0.95 | EPA/ASCE | 0.1–500 MGD |
| Wastewater treatment | Capacity (MGD) | 0.68–0.78 | 0.88–0.94 | EPA/ASCE | 0.1–500 MGD |
| Water pipeline | Dia (in) × Len | 0.85–0.95(L) | 0.90–0.96 | Municipal bids | 4–96 in |
| Sewer pipeline | Dia (in) × Len | 0.85–0.95(L) | 0.88–0.94 | Municipal bids | 8–120 in |
| Pump station | Capacity (GPM) | 0.55–0.65 | 0.85–0.92 | Published ref. | 100–100K GPM |
| Storage (at-grade) | Volume (MG) | 0.65–0.75 | 0.82–0.90 | Municipal | 0.1–50 MG |
| Storage (elevated) | Volume (MG) | 0.50–0.60 | 0.80–0.88 | Published ref. | 0.1–5 MG |

### 5.2.3 Buildings and Structures

| Facility | Size Param | Exponent | R² | Source |
| --- | --- | --- | --- | --- |
| Office building | Gross SF | 0.88–0.95 | 0.88–0.95 | RSMeans/Dodge |
| Warehouse | Gross SF | 0.90–0.98 | 0.90–0.96 | RSMeans/Dodge |
| School (K-12) | Gross SF | 0.85–0.92 | 0.85–0.93 | State DOE data |
| Hospital | Gross SF | 0.80–0.88 | 0.82–0.90 | AHA/FGI data |
| Parking structure | # Spaces | 0.85–0.92 | 0.88–0.94 | Published ref. |

### 5.2.4 Transportation

| Facility | Size Param | Exponent | R² | Source |
| --- | --- | --- | --- | --- |
| Highway (rural 2-lane) | Length (mi) | 0.92–0.98 | 0.92–0.97 | FHWA bid data |
| Highway (urban multi) | Lane-miles | 0.88–0.95 | 0.85–0.93 | FHWA bid data |
| Bridge (steel) | Deck area (SF) | 0.75–0.85 | 0.82–0.90 | FHWA NBI |
| Bridge (concrete) | Deck area (SF) | 0.78–0.88 | 0.84–0.92 | FHWA NBI |
| Tunnel (rock TBM) | Dia × Length | 0.70–0.82(D) | 0.75–0.88 | Case studies |
| Tunnel (soft ground) | Dia × Length | 0.75–0.85(D) | 0.70–0.85 | Case studies |

## 5.3 Parametric Model Implementation

class ParametricModel(BaseModel):

facility_type: str

size_parameter: str

size_unit: str

exponent: float

exponent_range: Tuple[float, float]

reference_cost: Decimal

reference_size: Decimal

reference_date: date

reference_location: str

valid_range: Tuple[Decimal, Decimal]

r_squared: Tuple[float, float]

source: str

complexity_factors: Dict[str, float]

def estimate(self, target_size, location_factor=1.0,

escalation_factor=1.0, complexity='average'):

# Range check with warning

if target_size < self.valid_range[0] or target_size > self.valid_range[1]:

warnings.warn(f'Size {target_size} outside valid range')

ratio = float(target_size / self.reference_size)

base = float(self.reference_cost) * (ratio ** self.exponent)

comp = self.complexity_factors.get(complexity, 1.0)

adjusted = base * float(location_factor) * float(escalation_factor) * comp

# Range from exponent uncertainty

low = float(self.reference_cost) * (ratio ** self.exponent_range[1]) * 0.85

high = float(self.reference_cost) * (ratio ** self.exponent_range[0]) * 1.15

return ParametricResult(

point_estimate=round(adjusted, 2),

low_estimate=round(low, 2),

high_estimate=round(high, 2),

confidence=0.7 if self._in_range(target_size) else 0.4,

aace_class_max=4,

)

## 5.4 Complexity Adjustment Factors

Parametric models assume average conditions. Complexity factors adjust for project-specific deviations.

| Factor Category | Simple | Average | Complex | Extreme |
| --- | --- | --- | --- | --- |
| Site access | 0.90 | 1.00 | 1.10–1.20 | 1.30–1.50 |
| Subsurface conditions | 0.90–0.95 | 1.00 | 1.10–1.25 | 1.30–1.60 |
| Environmental constraints | 0.95 | 1.00 | 1.10–1.20 | 1.25–1.50 |
| Regulatory complexity | 0.95 | 1.00 | 1.05–1.15 | 1.15–1.30 |
| Seismic requirements | 0.95 | 1.00 | 1.10–1.20 | 1.20–1.40 |
| Schedule compression | 0.95 | 1.00 | 1.10–1.20 | 1.20–1.40 |
| Remote/limited infra | 0.95 | 1.00 | 1.15–1.30 | 1.40–1.80 |
| Security requirements | 1.00 | 1.00 | 1.05–1.15 | 1.15–1.30 |

Combining Factors: Multiple complexity factors are multiplied, not added. Difficult subsurface (1.20) + remote location (1.30) = 1.20 × 1.30 = 1.56, not 1.50. This reflects the compounding nature of project complexity.

IMPORTANT: The subsurface conditions factor is the primary GeoLab integration point for parametric estimates. GeoLab classification data drives factor selection: mixed rock/soil with weathered zones warrants 1.30-1.60; uniform dense sand gets 0.90-0.95.

# 6. Contingency Analysis Methods

Contingency is an allowance for uncertainty in cost estimates—it is not a reserve for scope changes. The ENGR-KB contingency engine supports five methods ranging from simple percentage-based approaches to full Monte Carlo simulation. The appropriate method depends on AACE class and risk profile.

## 6.1 Method 1: Fixed Percentage

CE-CTG-001: AACE Class-Based Percentage

Contingency = Base Estimate × Contingency %

| AACE Class | Range | Default | When to Use |
| --- | --- | --- | --- |
| Class 5 | 30–50% | 40% | Screening, very early estimates |
| Class 4 | 20–35% | 25% | Feasibility, conceptual |
| Class 3 | 10–25% | 15% | Budget authorization |
| Class 2 | 5–15% | 10% | Control estimates |
| Class 1 | 3–10% | 5% | Definitive, check estimates |

Limitations: Fixed percentage over-allocates on well-understood work and under-allocates on high-risk items. Provides no insight into which items drive uncertainty. Use only for Class 4-5 or as a quick reasonableness check.

## 6.2 Method 2: Line-Item Risk Assessment

CE-CTG-002: Item-Level Contingency by Risk

Total Contingency = Σ (Line Item Cost × Line Item Contingency %)

| Risk Level | Pct | Criteria | Examples |
| --- | --- | --- | --- |
| Very Low | 2–5% | Well-defined, firm pricing, repetitive | Standard concrete, pipe installation |
| Low | 5–10% | Standard work, good historical data | Common earthwork, paving |
| Moderate | 10–20% | Some quantity/method uncertainty | Foundation work, dewatering |
| High | 20–35% | Significant unknowns, limited data | Rock excavation, contaminated soil |
| Very High | 35–50% | Major uncertainties, novel methods | Ground improvement, mixed-face tunnel |

## 6.3 Method 3: Range Estimating (Three-Point)

CE-CTG-003: PERT Three-Point Estimate

For each uncertain item, estimate three values:

- Optimistic (O): Best realistic case

- Most Likely (M): Expected under normal conditions

- Pessimistic (P): Worst realistic case

Expected Value: E = (O + 4M + P) / 6

Standard Deviation: σ = (P - O) / 6

Variance: σ² = ((P - O) / 6)²

For total estimate (assuming independence):

Total E = Σ E_i

Total σ = √(Σ σ_i²)

P80 = Total E + 0.842 × Total σ

P90 = Total E + 1.282 × Total σ

NOTE: Independence assumption is often violated. Material price increases affect all material items; weather delays affect all outdoor activities. Monte Carlo (Method 5) handles correlations explicitly.

## 6.4 Method 4: Expected Monetary Value

CE-CTG-004: Risk-Event-Based Contingency (EMV)

Contingency = Σ (P(risk_i) × Cost_Impact_i)

| Risk Event | Probability | Impact | EMV |
| --- | --- | --- | --- |
| Unexpected rock in excavation | 25% | $450,000 | $112,500 |
| Contaminated soil—special disposal | 15% | $280,000 | $42,000 |
| Dewatering exceeds planned capacity | 20% | $180,000 | $36,000 |
| Concrete price escalation >10% | 30% | $120,000 | $36,000 |
| Permit delays—2 month extension | 20% | $250,000 | $50,000 |
| Differing site conditions claim | 10% | $500,000 | $50,000 |
| Total EMV Contingency |  |  | $326,500 |

## 6.5 Method 5: Monte Carlo Simulation

CE-CTG-005: Probabilistic Cost via Monte Carlo

Generates a probability distribution of total project cost by randomly sampling from uncertainty distributions over thousands of iterations.

class CostMonteCarloConfig(BaseModel):

iterations: int = 10000

seed: Optional[int]

confidence_levels: List[float] = [0.50, 0.80, 0.85, 0.90, 0.95]

item_distributions: List[CostItemDistribution]

correlation_groups: List[CorrelationGroup]

class CostItemDistribution(BaseModel):

line_item_id: str

distribution: Literal['triangular','pert','normal','lognormal','uniform']

low: Decimal

most_likely: Decimal

high: Decimal

class CorrelationGroup(BaseModel):

name: str              # 'material_prices', 'labor_market'

item_ids: List[str]

correlation: float     # 0.0 to 1.0

class MonteCarloResult(BaseModel):

iterations_run: int

convergence_achieved: bool

p50: Decimal

p80: Decimal

p85: Decimal

p90: Decimal

p95: Decimal

mean: Decimal

std_dev: Decimal

contingency_at_p80: Decimal

contingency_at_p90: Decimal

sensitivity: Dict[str, float]   # item -> Spearman correlation

top_risk_drivers: List[str]

Agent Integration: The agent uses Monte Carlo results to validate contingency. If P80 simulation contingency differs from applied contingency by >20%, the agent flags for review. Sensitivity analysis identifies which items drive uncertainty.

## 6.6 Contingency Method Selection Guide

| AACE Class | Recommended Method(s) | Rationale |
| --- | --- | --- |
| Class 5 | Fixed Percentage | Insufficient detail for item-level analysis |
| Class 4 | Fixed % + EMV for known risks | Some risk events identifiable at concept |
| Class 3 | Line-Item + Range Estimating | Enough detail for item-level risk |
| Class 2 | Range Estimating + Monte Carlo | Detailed enough for probabilistic analysis |
| Class 1 | Monte Carlo + EMV | Full probabilistic with explicit risk events |

# 7. Earthwork Cost Estimating & GeoLab Integration

GEOLAB BRIDGE

The earthwork module is the primary integration between GeoLab lab data and ENGR-KB cost estimating. Soil properties from testing directly drive equipment selection, production rates, and unit costs.

## 7.1 Volume Conversion Equations

Earthwork volumes must be tracked through three states: bank (in-place), loose (hauled), and compacted (placed). Incorrect conversions are among the most common and costly earthwork estimating errors.

CE-EW-001: Bank to Loose

LCY = BCY × (1 + Swell Factor)

CE-EW-002: Bank to Compacted

CCY = BCY × (1 - Shrinkage Factor)

CE-EW-003: Load Factor

Load Factor = 1 / (1 + Swell Factor)

CE-EW-004: Density-Based Conversion (with GeoLab Proctor)

CCY = BCY × (Bank Density / Required Compacted Density)

### 7.1.1 Swell & Shrinkage by Soil Type (GeoLab-Derived)

| USCS | Description | Swell % | Shrink % | Load Factor | GeoLab Data |
| --- | --- | --- | --- | --- | --- |
| GW | Well-graded gravel | 10–12% | 5–8% | 0.89–0.91 | Gradation, Proctor |
| GP | Poorly-graded gravel | 10–14% | 5–10% | 0.88–0.91 | Gradation, Proctor |
| GM | Silty gravel | 12–15% | 8–12% | 0.87–0.89 | Grad, Atterberg, Proctor |
| GC | Clayey gravel | 12–16% | 8–14% | 0.86–0.89 | Grad, Atterberg, Proctor |
| SW | Well-graded sand | 12–15% | 8–12% | 0.87–0.89 | Gradation, Proctor |
| SP | Poorly-graded sand | 12–15% | 8–14% | 0.87–0.89 | Gradation, Proctor |
| SM | Silty sand | 15–18% | 10–15% | 0.85–0.87 | Grad, Atterberg, Proctor |
| SC | Clayey sand | 15–20% | 10–16% | 0.83–0.87 | Grad, Atterberg, Proctor |
| ML | Low-plasticity silt | 18–25% | 12–18% | 0.80–0.85 | Atterberg, Proctor, wc |
| CL | Low-plasticity clay | 20–30% | 12–20% | 0.77–0.83 | Atterberg, Proctor, wc |
| MH | High-plasticity silt | 25–35% | 15–25% | 0.74–0.80 | Atterberg, Proctor, wc |
| CH | High-plasticity clay | 25–40% | 15–28% | 0.71–0.80 | Atterberg, Proctor, wc |
| OL/OH | Organic soils | 30–50% | 20–35% | 0.67–0.77 | Organic content, Proctor |
| Rock | Blasted rock | Shrinks -25 to -10% | N/A | 1.11–1.33 | UCS, RQD, joints |

IMPORTANT: When GeoLab Proctor data is available, the system calculates exact swell/shrinkage from measured bank density and required compacted density rather than table lookups. Table values serve as defaults or validation checks.

## 7.2 Excavation Classification & Unit Costs

Excavation difficulty and cost depend primarily on material type. GeoLab classification drives method and unit cost selection.

| Classification | GeoLab Criteria | Method | Cost ($/CY) | Basis |
| --- | --- | --- | --- | --- |
| Common Excavation | GW,GP,SW,SP,SM,ML (N<30) | Standard excavator | $4–$12 | Public bid tabs |
| Firm Excavation | GC,SC,CL,CH (N=30-50) | Heavy excav., ripping | $8–$18 | Public bid tabs |
| Hard Excavation | Dense soils (N>50), soft rock | Hoe-ram, heavy rip | $15–$35 | Public bid tabs |
| Rock (rippable) | UCS < 7,000 psi, fractured | Ripper-equipped dozer | $20–$45 | Public bid tabs |
| Rock (blasting) | UCS > 7,000 psi, competent | Drill & blast + muck | $30–$75 | Public bid tabs |
| Wet Excavation | Below WT, k > 10⁻⁴ cm/s | Clamshell, dewatering | $15–$40 | USACE data |
| Contaminated | Hazardous (RCRA/CERCLA) | Special handling | $40–$200+ | Site-specific |
| Structural Excav. | Foundation/footing | Precision grading | $12–$25 | Public bid tabs |

Cost Range Note: 2024 reference ranges, Denver/Front Range basis, moderate conditions. Add $0.15-0.50/CY per 100 ft haul distance. Ranges represent 25th-75th percentile of public bid tabulations.

## 7.3 Haul Cost Equations

CE-EW-005: Truck Haul Cost

Haul Cost/CY = (Truck $/hr × Cycle Time) / Truck Capacity (LCY)

CE-EW-006: Haul Cycle Time

Cycle (min) = Load + Haul + Dump + Return + Spot/Delay

| Component | Formula | Typical Values |
| --- | --- | --- |
| Load Time | Truck Cap (LCY) / Loader Output (LCY/min) | 2–5 min |
| Haul Time | Haul Distance / Loaded Speed | Speed by grade/surface |
| Dump Time | Fixed per type | 0.5–2 min |
| Return Time | Return Distance / Empty Speed | 1.2–1.5× loaded speed |
| Spot/Delay | Fixed estimate | 0.5–1.5 min |

### 7.3.1 Haul Speed vs. Grade and Surface

| Road Surface | Grade | Loaded (mph) | Empty (mph) |
| --- | --- | --- | --- |
| Paved highway | Level (0–2%) | 35–45 | 40–50 |
| Paved highway | Moderate (3–6%) | 20–30 | 35–45 |
| Gravel (maintained) | Level (0–2%) | 20–30 | 25–35 |
| Gravel (maintained) | Moderate (3–6%) | 12–20 | 20–30 |
| Gravel (maintained) | Steep (7–10%) | 8–15 | 15–25 |
| Dirt (rough) | Level (0–2%) | 10–20 | 15–25 |
| Dirt (rough) | Moderate (3–6%) | 8–12 | 10–20 |
| Pit/quarry haul road | Variable | 8–15 | 12–20 |

## 7.4 Compaction Cost Equations

CE-EW-007: Compaction Production Rate

Production (CCY/hr) = (Width × Speed × Lift × Eff) / (Passes × 27)

| Variable | Description | Depends On |
| --- | --- | --- |
| Width | Effective drum width (ft) | Roller type, minus overlap |
| Speed | Roller travel speed (ft/hr) | Soil type, roller type (2–6 mph) |
| Lift | Compacted lift thickness (ft) | Soil type, compactor, spec requirement |
| Efficiency | Operating efficiency factor | 0.75–0.90 typical |
| Passes | Number of passes required | Soil type, compactor, spec density |
| 27 | CF per CY (unit conversion) | Constant |

### 7.4.1 Compaction Parameters by Soil Type

| USCS | Compactor Type | Lift (in) | Passes | Speed (mph) | Notes |
| --- | --- | --- | --- | --- | --- |
| GW, GP | Vibratory smooth drum | 8–12 | 3–5 | 3–5 | Excellent compaction response |
| SW, SP | Vibratory smooth drum | 8–12 | 3–5 | 3–5 | May need moisture addition |
| GM, SM | Vibratory or sheepsfoot | 6–8 | 4–6 | 2–4 | Moisture sensitive |
| GC, SC | Sheepsfoot or padfoot | 6–8 | 4–8 | 2–4 | Knead to break clods |
| ML | Sheepsfoot | 4–6 | 6–8 | 2–3 | Very moisture sensitive |
| CL | Sheepsfoot | 4–6 | 6–10 | 2–3 | Narrow moisture range |
| CH | Sheepsfoot | 4–6 | 8–12 | 2–3 | Very narrow moisture range |
| MH | Sheepsfoot | 4–6 | 8–12 | 2–3 | Difficult to compact |

IMPORTANT: GeoLab Proctor test results directly determine the target density and optimal moisture content. The compaction specification (e.g., 95% of Standard Proctor) sets the pass count needed. Lab moisture content vs. optimum determines whether moisture conditioning (wetting or drying) costs apply.

## 7.5 Moisture Conditioning Costs

CE-EW-008: Moisture Conditioning Cost

When GeoLab moisture content data shows material is too wet or too dry relative to optimum:

| Condition | GeoLab Trigger | Required Action | Added Cost ($/CY) |
| --- | --- | --- | --- |
| Too dry (w < OMC - 3%) | Lab moisture < optimum - 3% | Water truck application, mixing | $0.50–$2.00 |
| Slightly dry (w < OMC - 1%) | Lab moisture < optimum - 1% | Light watering during placement | $0.25–$0.75 |
| At optimum (±1%) | Lab moisture ≈ optimum | No conditioning needed | $0.00 |
| Slightly wet (w > OMC + 2%) | Lab moisture > optimum + 2% | Aeration, scarifying, drying time | $1.00–$3.00 |
| Too wet (w > OMC + 4%) | Lab moisture > optimum + 4% | Extensive drying, soil amendment | $2.00–$8.00 |
| Saturated (w >> OMC) | Near or above saturation | Dewatering, chemical stabilization | $5.00–$20.00+ |

## 7.6 Earthwork Mass Haul Optimization

CE-EW-009: Mass Diagram Analysis

The mass diagram (Bruckner diagram) optimizes cut-fill balance to minimize haul distances:

Cumulative Volume at Station n = Σ (Cut_i - Fill_i) for i = 0 to n

Average Haul Distance = Area under mass curve / Volume moved

Free Haul = Volume moved within free-haul distance (typically 500–1000 ft)

Overhaul = Volume moved beyond free-haul distance × excess distance

CE-EW-010: Overhaul Cost

Overhaul Cost = Overhaul Volume (CY) × Overhaul Distance (sta) × Overhaul Rate ($/CY-sta)

| Parameter | Typical Value | Notes |
| --- | --- | --- |
| Free-haul distance | 500–1,000 ft | Contract-defined, varies by agency |
| Overhaul rate | $0.10–$0.50 / CY-station | Per CY per 100-ft station of excess haul |
| Economic haul limit | 2,000–5,000 ft | Beyond this, borrow is cheaper than overhaul |
| Borrow cost (delivered) | $8–$25 / CY | Includes purchase, load, haul, place |
| Waste/disposal cost | $5–$20 / CY | Includes load, haul, disposal fee |

## 7.7 Earthwork Data Model

class EarthworkEstimate(BaseModel):

"""Complete earthwork cost estimate with GeoLab integration."""

project_id: str

geolab_project_id: Optional[str]  # Link to GeoLab project

# Site Data

site_area: Decimal               # acres

topography: str                  # 'flat', 'rolling', 'steep'

water_table_depth: Optional[Decimal]  # ft below surface

# Volume Summary

total_cut: Decimal               # BCY

total_fill: Decimal              # CCY

net_volume: Decimal              # + = excess cut, - = borrow needed

waste_volume: Decimal            # CY to waste

borrow_volume: Decimal           # CY to import

# Soil Zones (from GeoLab boring data)

soil_zones: List[SoilZone]

# Cost Components

clearing_grubbing: Optional[LineItem]

stripping: Optional[LineItem]

excavation_items: List[ExcavationItem]

haul_items: List[HaulItem]

fill_placement: List[FillItem]

compaction_items: List[CompactionItem]

moisture_conditioning: List[LineItem]

dewatering: Optional[LineItem]

erosion_control: Optional[LineItem]

class SoilZone(BaseModel):

zone_id: str

uscs_class: str                  # From GeoLab classification

volume_bcy: Decimal

bank_density: Decimal            # pcf, from GeoLab Proctor

optimum_moisture: Decimal        # %, from GeoLab Proctor

field_moisture: Decimal          # %, from GeoLab moisture tests

proctor_max_density: Decimal     # pcf

swell_factor: Decimal            # computed or table lookup

shrinkage_factor: Decimal

excavation_class: str            # common/firm/hard/rock

compactability: str              # excellent/good/fair/poor

geolab_specimen_ids: List[str]   # Links to GeoLab specimens

# 8. Labor Rate Structure & Markup

## 8.1 Labor Burden Rate Calculation

CE-LAB-001: Fully Burdened Labor Rate

Burden Rate = Base Wage × (1 + FICA + FUTA + SUTA + Workers Comp + Benefits)

| Burden Component | Typical % | Notes |
| --- | --- | --- |
| FICA (Social Security + Medicare) | 7.65% | Employer match, on first $168,600 (2024) |
| FUTA (Federal Unemployment) | 0.6% | On first $7,000 per employee |
| SUTA (State Unemployment) | 1–6% | Varies by state and employer rating |
| Workers Compensation | 5–30% | Varies dramatically by trade/state |
| Health Insurance | 8–15% | Highly variable by plan |
| Pension/401k | 3–8% | Union vs. non-union varies widely |
| Vacation/Holiday | 4–8% | Paid time off |
| Training/Apprentice | 1–4% | Union requirement in many trades |
| Total Typical Burden | 30–70% | Heavy civil: 45-65% typical |

### 8.1.1 Davis-Bacon Prevailing Wage Rates

Federal and many state projects require Davis-Bacon prevailing wage rates. These are published by the DOL and vary by county and trade. Representative heavy construction rates (illustrative, Denver metro area):

| Trade | Base Wage ($/hr) | Fringe ($/hr) | Total ($/hr) | Typical Burden % |
| --- | --- | --- | --- | --- |
| Operating Engineer (crane) | $38–$48 | $18–$24 | $56–$72 | 55–65% |
| Operating Engineer (dozer) | $35–$45 | $17–$22 | $52–$67 | 55–65% |
| Laborer (general) | $22–$30 | $12–$18 | $34–$48 | 50–60% |
| Laborer (skilled) | $25–$34 | $13–$19 | $38–$53 | 50–60% |
| Carpenter | $30–$40 | $16–$22 | $46–$62 | 55–65% |
| Ironworker | $35–$45 | $18–$24 | $53–$69 | 55–65% |
| Cement Mason | $28–$38 | $15–$20 | $43–$58 | 50–60% |
| Teamster (truck driver) | $30–$40 | $16–$22 | $46–$62 | 50–60% |
| Electrician | $35–$48 | $18–$26 | $53–$74 | 55–65% |
| Pipe Fitter/Plumber | $38–$50 | $20–$28 | $58–$78 | 55–70% |

IMPORTANT: These are representative ranges only. Actual Davis-Bacon rates are county-specific and published in DOL Wage Determinations. The system can import current wage determinations via the DOL API (sam.gov) for precise labor costing on federal projects.

## 8.2 Markup Structure

CE-MKP-001: Contractor Markup Calculation

Bid Price = Direct Cost × (1 + Overhead %) × (1 + Profit %)

| Markup Component | Typical Range | Description |
| --- | --- | --- |
| Home Office Overhead | 3–8% | Corporate G&A, office rent, admin staff |
| Field/Job Overhead | 8–15% | Superintendent, field office, temp utilities, safety |
| Profit | 5–15% | Varies by competition, risk, market conditions |
| Bond (if not in indirect) | 0.5–2.5% | Performance and payment bond premiums |

### 8.2.1 Change Order Markup Rates

Change order markup is often contractually defined. Common provisions:

| Work By | Overhead | Profit | Source |
| --- | --- | --- | --- |
| Contractor (self-performed) | 15% | 10% | FAR 52.243 / typical commercial |
| First-tier subcontractor | 15% | 10% | Common contract provision |
| Lower-tier subcontractor | 15% | 10% | Common contract provision |
| Contractor on sub work | 5% | 5% | Markup on sub’s price |

IMPORTANT: For federal contracts, FAR clause 52.243 defines change order pricing. Many state/local agencies use similar provisions. The agent uses contract-specific markup rates when processing change orders.

## 8.3 Equipment Hourly Rate Calculation

CE-EQP-001: Equipment Hourly Owning + Operating Cost

Hourly Rate = Ownership Cost/hr + Operating Cost/hr

| Cost Component | Formula | Category |
| --- | --- | --- |
| Depreciation | (Purchase Price - Salvage) / Useful Life Hours | Ownership |
| Interest/Cost of Money | ((P + S) / 2) × Interest Rate / Annual Hours | Ownership |
| Insurance | Value × Insurance Rate / Annual Hours | Ownership |
| Property Tax | Value × Tax Rate / Annual Hours | Ownership |
| Fuel | HP × Load Factor × Specific Fuel Consumption × $/gal | Operating |
| Lubricants | Typically 10–15% of fuel cost | Operating |
| Tires (rubber-tired) | Tire Cost / Tire Life Hours | Operating |
| Repair Reserve | 50–80% of depreciation rate | Operating |
| Ground Engaging (GET) | Bucket teeth, cutting edges cost / life | Operating |

USACE Method: USACE EP 1110-1-8 (Construction Equipment Ownership and Operating Expense Schedule) provides standardized rates for government estimates. The system implements this methodology as the default, with override capability for user-specific fleet data.

# 9. Complete Equation Catalog

This section catalogs all equations in the Cost Estimating domain with unique identifiers, formulas, input/output parameters, and source references.

## 9.1 Core Estimating Equations

| ID | Name | Formula | Source |
| --- | --- | --- | --- |
| CE-001 | Total Direct Cost | Σ(Qty × Unit Cost × Waste × Productivity) | AACE RP 10S-90 |
| CE-002 | Extended Line Item | Quantity × Unit Price | Standard practice |
| CE-003 | Assembly Cost | Σ(Component Qty × Component Unit Cost) | Standard practice |
| CE-004 | Indirect Cost | Σ(Category Rate × Basis) or Lump Sum | Project-specific |
| CE-005 | Total Project Cost | Direct + Indirect + Contingency + Markup | AACE framework |

## 9.2 Escalation & Location Equations

| ID | Name | Formula | Source |
| --- | --- | --- | --- |
| CE-ESC-001 | Simple Escalation | Cost × (Index_target / Index_base) | ENR methodology |
| CE-ESC-002 | Component Escalation | Σ(Component × Component_Index_Ratio) | Best practice |
| CE-ESC-003 | Midpoint Escalation | Cost × (Index_midpoint / Index_base) | AACE RP 25R-03 |
| CE-ESC-004 | Cash Flow Escalation | Σ(Monthly_Spend × Monthly_Index_Ratio) | AACE RP 25R-03 |
| CE-LOC-001 | Location Adjustment | Cost × (Factor_target / Factor_base) | RSMeans methodology |
| CE-LOC-002 | Component Location | Σ(Component × Component_Loc_Factor) | Best practice |
| CE-COMB-001 | Combined Adjust. | Cost × Escalation_Factor × Location_Factor | Standard practice |

## 9.3 Parametric Equations

| ID | Name | Formula | Source |
| --- | --- | --- | --- |
| CE-PAR-001 | Power-Law Model | C = C_ref × (Q/Q_ref)^n × Factors | AACE RP 28R-03 |
| CE-PAR-002 | Complexity Adjust. | Π(Factor_i) for all applicable factors | AACE/published |
| CE-PAR-003 | Range from Exponent | Low = C_ref×(Q/Q_ref)^n_high×0.85 | Statistical |

## 9.4 Contingency Equations

| ID | Name | Formula | Source |
| --- | --- | --- | --- |
| CE-CTG-001 | Fixed Percentage | Base × Contingency% | AACE RP 40R-08 |
| CE-CTG-002 | Line-Item Risk | Σ(Item Cost × Item Contingency%) | AACE RP 40R-08 |
| CE-CTG-003 | PERT Expected | E = (O+4M+P)/6; σ = (P-O)/6 | PERT methodology |
| CE-CTG-004 | Expected Mon. Value | Σ(P(risk) × Impact) | Risk analysis |
| CE-CTG-005 | Monte Carlo | N iterations sampling distributions | AACE RP 41R-08 |

## 9.5 Earthwork Equations

| ID | Name | Formula | Source |
| --- | --- | --- | --- |
| CE-EW-001 | Bank to Loose | LCY = BCY × (1 + Swell) | Earthwork practice |
| CE-EW-002 | Bank to Compacted | CCY = BCY × (1 - Shrinkage) | Earthwork practice |
| CE-EW-003 | Load Factor | LF = 1 / (1 + Swell) | Earthwork practice |
| CE-EW-004 | Density Conversion | CCY = BCY × (γ_bank / γ_compact) | From GeoLab Proctor |
| CE-EW-005 | Haul Cost | ($/hr × Cycle) / Truck Cap | USACE/Caterpillar |
| CE-EW-006 | Cycle Time | Load+Haul+Dump+Return+Spot | Caterpillar PHB |
| CE-EW-007 | Compaction Rate | (W×S×L×E) / (P×27) | Caterpillar PHB |
| CE-EW-008 | Moisture Conditioning | Cost based on Δw from optimum | Field practice |
| CE-EW-009 | Mass Diagram | Σ(Cut_i - Fill_i) cumulative | Highway engineering |
| CE-EW-010 | Overhaul Cost | Vol × ΔDistance × Rate | Highway practice |

## 9.6 Labor & Equipment Equations

| ID | Name | Formula | Source |
| --- | --- | --- | --- |
| CE-LAB-001 | Burden Rate | Wage × (1 + ΣBurden%) | Payroll practice |
| CE-MKP-001 | Contractor Markup | Direct × (1+OH%) × (1+Profit%) | Standard practice |
| CE-EQP-001 | Equipment Rate | Ownership/hr + Operating/hr | USACE EP 1110-1-8 |
| CE-EQP-002 | Fuel Consumption | HP × LF × SFC × $/gal | Caterpillar PHB |
| CE-EQP-003 | Fleet Balance | N_trucks = Cycle_truck / Cycle_loader | Production analysis |

## 9.7 Equation Count Summary

| Category | Count | Phase |
| --- | --- | --- |
| Core Estimating | 5 | 1 |
| Escalation & Location | 7 | 1 |
| Parametric | 3 | 1-2 |
| Contingency | 5 | 1-2 |
| Earthwork | 10 | 1 |
| Labor & Equipment | 5 | 1 |
| TOTAL | 35 | Phase 1 core |

Additional equations will be added in Phase 2 (concrete/structural estimating, utility cost models, specialty subcontractor pricing) and Phase 3 (parametric model library expansion, AI-assisted cost prediction from historical patterns).

# 10. Reference Data Tables Summary

The Cost Estimating domain ships with the following reference data tables. All tables carry metadata including source, date, geographic basis, and confidence level.

| Data Table | Records | Source Basis | Update |
| --- | --- | --- | --- |
| Earthwork Unit Cost Ranges | ~80 | Public bid tabs, USACE/USBR | Annual + user cal. |
| Concrete Unit Cost Ranges | ~60 | Public bid tabs, published | Annual + user cal. |
| Utility Unit Cost Ranges | ~50 | Municipal bid tabs | Annual + user cal. |
| Equipment Specifications | ~200 | Manufacturer published | As released |
| Equipment Hourly Rates | ~200 | USACE EP 1110-1-8 method | Annual recalc |
| Labor Rates (Davis-Bacon) | ~50 regions | DOL Wage Determinations | Annual (DOL API) |
| Swell/Shrinkage Factors | ~15 soil types | Published references | Static |
| Compaction Parameters | ~15 soil types | Caterpillar/published | Static |
| City Cost Indices | ~50 cities | Published references | Annual |
| ENR CCI/BCI History | ~30 years | Engineering News-Record | Monthly |
| BLS PPI Components | ~20 categories | Bureau of Labor Statistics | Monthly |
| Parametric Coefficients | ~40 facility types | AACE/USBR/USACE/EPA | Periodic |
| Complexity Factors | ~8 categories | Published/practice | Static |
| Crew Compositions | ~30 standard crews | RSMeans/practice | Annual |
| Productivity Rates | ~150 activities | USACE/Caterpillar/published | User calibration |

IMPORTANT: All cost data represents publicly available reference ranges, not proprietary databases. The system is designed for calibration with user historical data and optional commercial database integration (RSMeans API, etc.). Cost data should be validated against local market conditions before use in formal estimates.

## 10.1 Data Quality & Confidence Framework

Every data point carries a confidence score reflecting data quality and recency:

| Confidence Range | Meaning | Data Characteristics |
| --- | --- | --- |
| 0.90–1.00 | Very High | Current vendor quote, recent (<6 mo) bid tab, lab-measured |
| 0.75–0.89 | High | Published reference (<2 yr), calibrated historical, DOL rates |
| 0.60–0.74 | Moderate | Published reference (2-5 yr), regional average, parametric |
| 0.40–0.59 | Low | Aged data (>5 yr), extrapolated, limited sample size |
| 0.20–0.39 | Very Low | Professional judgment, single data point, uncertain source |

Agent Behavior: The workflow agent factors confidence scores into validation. Estimates heavily reliant on low-confidence data (weighted avg confidence <0.60) are flagged for additional review. The agent also tracks which data items have the lowest confidence and suggests where additional pricing effort would most reduce estimate uncertainty.