ENGR-KB

Engineering Knowledge Base

Specifications

MasterFormat Taxonomy, Standards Engine, Compliance & GeoLab Integration

v1.0  |  February 2026

ENGR-KB Document Series  |  Document 3 of 6

DRAFT — INTERNAL USE ONLY

# Table of Contents

# 1. Specifications Domain Overview

The Specifications domain provides a structured engine for managing construction specifications organized per CSI MasterFormat 2018. It handles specification composition, cross-referencing, compliance checking, submittal tracking, and integration with cost estimating and project management. The engine maintains the complete specification hierarchy with metadata on applicable standards, testing requirements, and quality assurance provisions.

Core Design Principle: Specifications are the contractual bridge between design intent and construction execution. Every requirement in a specification should be measurable, verifiable, and traceable to a standard or design criterion. The engine enforces this principle through structured data models that link requirements to verification methods, test standards, and acceptance criteria.

## 1.1 Scope of Coverage

The specifications engine covers the full CSI MasterFormat structure with deep coverage in geotechnical and heavy civil divisions. Coverage depth reflects relevance to GeoLab integration and the cost estimating domain.

| Coverage Level | Description | Divisions |
| --- | --- | --- |
| Comprehensive | Full section templates, all 3 parts, complete std refs | 01, 02, 03, 31, 32, 33 |
| Deep | Section templates with key provisions, major std refs | 05, 26, 35, 40, 41 |
| Moderate | Section outlines, critical requirements only | 07, 09, 22, 23, 27, 34 |
| Index Only | MasterFormat listing, no template content | All remaining divisions |

## 1.2 Key Capabilities

- Specification Composition: Build project-specific specifications from guide spec templates with intelligent defaults based on project type and GeoLab data.

- Cross-Reference Validation: Deterministically verify that all section cross-references resolve correctly and all referenced standards are current.

- Submittal Management: Track required submittals by section, review status, and resubmittal cycles.

- Compliance Checking: Compare contractor submittals and test results against specification requirements.

- Conflict Detection: Identify contradictory requirements across sections (AI-augmented).

- Cost Integration: Generate testing/inspection cost items from specification requirements.

## 1.3 Three-Part Section Format

All specifications follow the CSI three-part SectionFormat:

| Part | Title | Content | Engine Role |
| --- | --- | --- | --- |
| Part 1 | General | References, submittals, QA/QC, delivery/storage | Generates submittal list, links standards |
| Part 2 | Products | Materials, equipment, mixes, fabrication | Links to cost data, material specs |
| Part 3 | Execution | Preparation, installation, field QC, protection | Links to construction methods, testing freq. |

# 2. MasterFormat Taxonomy

The complete CSI MasterFormat 2018 taxonomy is maintained in the knowledge base. The following tables show the division/group/section hierarchy for divisions with deep or comprehensive coverage.

## 2.1 Division 01: General Requirements

Division 01 establishes project-wide administrative and procedural requirements. These provisions apply across all other divisions and are critical for QC/QA framework, testing protocols, and submittal procedures.

| Section | Title | Key Content | Agent Relevance |
| --- | --- | --- | --- |
| 01 10 00 | Summary | Work scope, contracts, owner-furnished items | Scope validation |
| 01 25 00 | Substitution Procedures | Product substitution rules, approval process | Substitution workflow |
| 01 31 00 | Project Management & Coordination | Meetings, schedules, coordination | Schedule integration |
| 01 33 00 | Submittal Procedures | Submittal format, review times, resubmittals | Submittal tracking engine |
| 01 35 00 | Special Procedures | Night work, noise limits, traffic control | Method constraints |
| 01 40 00 | Quality Requirements | QC/QA plan, testing lab qualifications | Testing cost generation |
| 01 42 00 | References | Standard editions, code applicability | Standard cross-ref engine |
| 01 45 00 | Quality Control | Inspection procedures, non-conformance | NCR workflow |
| 01 45 23 | Testing and Inspection Services | Testing frequency, lab requirements | GeoLab integration point |
| 01 50 00 | Temporary Facilities | Field offices, utilities, roads | Indirect cost generation |
| 01 57 00 | Temporary Controls | Erosion control, dust, SWPPP | Environmental compliance |
| 01 60 00 | Product Requirements | Product options, substitutions | Material cost validation |
| 01 70 00 | Execution and Closeout | Cleaning, waste disposal, as-builts | Closeout tracking |
| 01 78 00 | Closeout Submittals | O&M manuals, warranties, record docs | Closeout workflow |

## 2.2 Division 02: Existing Conditions

| Section | Title | Key Content | GeoLab Integration |
| --- | --- | --- | --- |
| 02 21 00 | Surveys | Boundary, topographic, as-built surveys | Site model input |
| 02 30 00 | Subsurface Investigation | Borings, test pits, sampling, in-situ testing | Primary GeoLab data source |
| 02 32 00 | Geotechnical Investigation | Lab testing program, geotechnical report | GeoLab report output |
| 02 41 00 | Demolition | Structural demo, salvage, disposal | Waste volume estimate |
| 02 51 00 | Chemical Soil Stabilization | Lime, cement, fly ash treatment | Lab mix design data |
| 02 61 00 | Removal of Underground Tanks | UST removal, contaminated soil | Contamination testing |
| 02 81 00 | Transportation/Disposal of Contaminated Soil | Characterization, manifests | Waste classification |

## 2.3 Division 03: Concrete

| Section | Title | Key Content | Testing Requirements |
| --- | --- | --- | --- |
| 03 10 00 | Concrete Forming | Form types, tolerances, stripping | Form survey, alignment check |
| 03 11 00 | Concrete Forming (structural) | Shoring, reshoring, form design | Shore load capacity verify |
| 03 20 00 | Concrete Reinforcing | Rebar, splice, cover, supports | Mill certs, placement inspect |
| 03 30 00 | Cast-in-Place Concrete | Mix design, placement, finishing, curing | Cylinder tests, slump, air, temp |
| 03 31 00 | Structural Concrete | Structural mix requirements | Compressive strength testing |
| 03 35 00 | Concrete Finishing | Broom, float, trowel, exposed agg | Surface tolerance checks |
| 03 39 00 | Concrete Curing | Wet cure, membrane, blankets | Cure temperature monitoring |
| 03 40 00 | Precast Concrete | Plant QC, erection, connections | Plant inspection, strength tests |
| 03 45 00 | Precast Architectural Concrete | Finish, color, tolerances | Mock-up approval |
| 03 60 00 | Grouting | Non-shrink, epoxy, cementitious | Cube/prism strength tests |
| 03 62 00 | Non-Shrink Grouting | Base plate grouting, equipment pads | Strength, expansion testing |

## 2.4 Division 31: Earthwork (Primary Geotech Division)

Division 31 is the most heavily instrumented division in ENGR-KB due to direct GeoLab integration. Every section links to specific lab test types and field verification procedures.

| Section | Title | Key Content | GeoLab Tests |
| --- | --- | --- | --- |
| 31 00 00 | Earthwork (General) | Definitions, earthwork classifications | Classification (USCS/AASHTO) |
| 31 05 13 | Soils for Earthwork | Soil types, borrow requirements | Gradation, Atterberg, organics |
| 31 05 16 | Aggregates for Earthwork | Base course, drain rock, filter | Gradation, LA Abrasion, SE |
| 31 10 00 | Site Clearing | Clear, grub, strip topsoil | N/A (survey verification) |
| 31 20 00 | Earth Moving | Cut, fill, grading, compaction | Proctor, moisture, density |
| 31 22 00 | Grading | Rough grading, fine grading, tolerances | Field density, grade survey |
| 31 23 00 | Excavation and Fill | Methods, lift thickness, moisture control | Proctor, field density, moisture |
| 31 23 16 | Excavation (unclassified) | All material types, no classification | Field identification |
| 31 23 17 | Excavation (classified) | Pay by material type (common/rock) | UCS, RQD for rock classification |
| 31 23 19 | Dewatering | Methods, discharge, monitoring | Permeability, piezometer data |
| 31 23 23 | Fill | Material requirements, placement | Proctor, gradation, moisture |
| 31 23 33 | Trenching & Backfilling | Pipe bedding, trench safety | Bedding gradation, backfill density |
| 31 25 00 | Erosion and Sedimentation Control | BMPs, SWPPP compliance | Soil erodibility (K-factor) |
| 31 30 00 | Earthwork Methods | Blasting, chemical stabilization | UCS, petrography |
| 31 32 00 | Soil Stabilization | Mechanical, chemical, geosynthetic | Lab mix design, CBR, UCS |
| 31 33 00 | Rock Stabilization | Rock bolts, shotcrete, mesh | RQD, joint mapping, UCS |
| 31 36 00 | Gabions | Gabion walls, mattresses | Rock gradation, durability |
| 31 40 00 | Shoring and Underpinning | Sheet pile, soldier pile, lagging | Lateral earth pressure params |
| 31 50 00 | Excavation Support | Slurry walls, soil nails, tiebacks | Shear strength, earth pressure |
| 31 60 00 | Special Foundations | Micropiles, ground anchors | Soil/rock strength, bond stress |
| 31 63 00 | Bored Piles | Drilled shafts, auger cast | Side/tip resistance from lab data |
| 31 66 00 | Special Foundation Elements | Specialty piles, caissons | Load test correlation |

## 2.5 Division 32: Exterior Improvements

| Section | Title | Key Content | GeoLab Tests |
| --- | --- | --- | --- |
| 32 10 00 | Bases, Ballasts, and Paving | Aggregate base, subbase | Gradation, Proctor, CBR |
| 32 11 00 | Base Courses | Crushed stone, recycled | Gradation, compaction |
| 32 12 00 | Flexible Paving (Asphalt) | HMA design, placement, compaction | Mix design, core density |
| 32 13 00 | Rigid Paving (Concrete) | PCC design, joints, finishing | Mix design, strength |
| 32 16 00 | Curbs, Gutters, Sidewalks | CIP concrete, extruded curb | Concrete strength tests |
| 32 31 00 | Fences and Gates | Chain link, security fence | Post embedment depth |
| 32 90 00 | Planting | Topsoil, seeding, planting | Topsoil quality testing |
| 32 92 00 | Turf and Grasses | Hydroseeding, sod | Soil fertility, pH |

## 2.6 Division 33: Utilities

| Section | Title | Key Content | GeoLab Tests |
| --- | --- | --- | --- |
| 33 05 00 | Common Work Results for Utilities | Trenching, bedding, backfill std | Backfill density, bedding grad. |
| 33 10 00 | Water Utilities | Water main, services, valves | Pipe bedding, thrust block |
| 33 30 00 | Sanitary Sewerage | Gravity sewer, manholes, services | Bedding, backfill, infiltration |
| 33 34 00 | Sanitary Force Mains | Pressure sewer, air release | Soil corrosivity testing |
| 33 40 00 | Storm Drainage | Storm pipe, inlets, detention | Percolation, permeability |
| 33 44 00 | Storm Utility Detention | Underground detention, BMPs | Permeability, porosity |
| 33 46 00 | Subdrainage | Foundation drains, underdrains | Filter gradation criteria |
| 33 51 00 | Natural Gas Distribution | Gas main, services, meter sets | Soil corrosivity |
| 33 70 00 | Electrical Utilities | Duct banks, handholes, conduit | Thermal resistivity testing |

## 2.7 Division 35: Waterway and Marine

| Section | Title | Key Content | GeoLab Tests |
| --- | --- | --- | --- |
| 35 20 00 | Dam Construction | Embankment dams, concrete dams | Full lab program |
| 35 31 00 | Dredging | Hydraulic, mechanical, disposal | Sediment classification |
| 35 42 00 | Waterway Bank Protection | Riprap, revetment, bioeng. | Rock gradation, durability |
| 35 43 00 | Waterway Scour Protection | Articulated mats, A-jacks | Scour velocity analysis |
| 35 51 00 | Levee Construction | Embankment, seepage control | Permeability, piping analysis |
| 35 71 00 | Constructed Wetlands | Liner, substrate, planting | Permeability, substrate testing |

# 3. Specification Data Models

Every specification section is represented as a structured Pydantic model that enables deterministic cross-referencing, compliance checking, and integration with cost estimating and project management domains.

## 3.1 Section Model

class SpecSection(BaseModel):

"""Complete specification section following CSI 3-part format."""

# Identification

number: str                    # e.g., '31 23 00'

title: str                     # 'Excavation and Fill'

division: int                  # 31

level: int                     # hierarchy depth (2=group, 3=section)

status: Literal['draft', 'review', 'approved', 'issued', 'superseded']

# Three-Part Content

part_1: Part1General

part_2: Part2Products

part_3: Part3Execution

# Cross-References

referenced_standards: List[StandardReference]

cross_referenced_sections: List[SectionCrossRef]

related_cost_codes: List[str]   # Links to cost estimating

related_schedule_activities: List[str]  # Links to PM domain

# Metadata

source_guide_spec: Optional[str]  # 'USACE', 'DOT_CO', 'custom'

revision: int = 1

last_modified: datetime

author: str

reviewer: Optional[str]

### 3.1.1 Part 1: General

class Part1General(BaseModel):

summary: Optional[str]         # Scope description

related_sections: List[SectionCrossRef]

references: List[StandardReference]

definitions: Dict[str, str]    # Term -> definition

submittals: List[SubmittalRequirement]

quality_assurance: QualityAssurance

delivery_storage: Optional[DeliveryRequirements]

project_conditions: Optional[ProjectConditions]

class QualityAssurance(BaseModel):

qualifications: List[str]       # Installer/manufacturer quals

certifications: List[str]       # Required certifications

regulatory: List[str]           # Permits, agency approvals

testing_lab_requirements: Optional[str]

mock_ups: List[MockUpRequirement]

pre_installation_meeting: bool = False

### 3.1.2 Part 2: Products

class Part2Products(BaseModel):

materials: List[MaterialRequirement]

equipment: List[EquipmentRequirement]

mixes: List[MixDesignRequirement]

fabrication: Optional[FabricationRequirement]

source_quality: Optional[SourceQualityRequirement]

class MaterialRequirement(BaseModel):

name: str

standard: str                   # 'ASTM C150'

type_grade: Optional[str]       # 'Type I/II'

properties: Dict[str, PropertyRequirement]

acceptable_products: List[str]  # Named products (or-equal)

substitution_allowed: bool = True

class PropertyRequirement(BaseModel):

property_name: str              # 'Compressive Strength'

test_method: str                # 'ASTM C39'

minimum: Optional[Decimal]

maximum: Optional[Decimal]

target: Optional[Decimal]

unit: str

at_age: Optional[str]           # '28 days'

### 3.1.3 Part 3: Execution

class Part3Execution(BaseModel):

preparation: List[str]          # Site/surface prep steps

installation_methods: List[InstallationMethod]

field_quality_control: FieldQC

tolerances: List[Tolerance]

protection: Optional[str]

cleaning: Optional[str]

class FieldQC(BaseModel):

testing_requirements: List[TestingRequirement]

inspection_requirements: List[InspectionRequirement]

acceptance_criteria: List[AcceptanceCriterion]

non_conformance_procedure: str

class TestingRequirement(BaseModel):

test_name: str                  # 'Field Density Test'

test_method: str                # 'ASTM D6938'

frequency: TestFrequency

acceptance_criterion: str        # '>=95% of max dry density'

action_on_failure: str           # 'Rework and retest'

responsible_party: Literal['contractor', 'owner', 'third_party']

geolab_test_type: Optional[str]  # Link to GeoLab test module

class TestFrequency(BaseModel):

basis: Literal['volume', 'area', 'length', 'time', 'lot', 'each']

quantity: Decimal               # e.g., 500

unit: str                       # e.g., 'CY'

minimum_per_day: Optional[int]  # At least N per day of work

minimum_per_lift: Optional[int] # At least N per lift

description: str                # '1 test per 500 CY of fill'

## 3.2 Submittal Model

Submittals are tracked from creation through review to final disposition. The system generates the submittal register automatically from specification section requirements.

class SubmittalRequirement(BaseModel):

submittal_type: SubmittalType

description: str

action: ReviewAction

timing: SubmittalTiming

spec_paragraph: str             # Source paragraph reference

standard_ref: Optional[str]

resubmittal_expected: bool = False

class SubmittalType(str, Enum):

SHOP_DRAWING = 'shop_drawing'

PRODUCT_DATA = 'product_data'

SAMPLE = 'sample'

DESIGN_DATA = 'design_data'

TEST_REPORT = 'test_report'

CERTIFICATE = 'certificate'

MANUFACTURERS_INSTRUCTIONS = 'manufacturers_instructions'

MIX_DESIGN = 'mix_design'

QUALIFICATION_DATA = 'qualification_data'

CLOSEOUT = 'closeout'

class ReviewAction(str, Enum):

APPROVAL = 'approval'               # Work cannot proceed without

APPROVAL_RESUBMIT = 'approval_resubmit'  # Requires resubmission

REVIEW = 'review'                    # Reviewed, no approval needed

INFORMATION = 'information'           # For information only

class SubmittalTiming(str, Enum):

BEFORE_ORDERING = 'before_ordering'

BEFORE_FABRICATION = 'before_fabrication'

BEFORE_INSTALLATION = 'before_installation'

BEFORE_CONCEALMENT = 'before_concealment'

WITH_CLOSEOUT = 'with_closeout'

ONGOING = 'ongoing'                  # e.g., test reports

### 3.2.1 Submittal Tracking Model

class Submittal(BaseModel):

"""Actual submittal instance (vs. requirement)."""

submittal_id: str

spec_section: str

requirement_ref: str             # Links to SubmittalRequirement

contractor_number: str           # Contractor's submittal number

description: str

date_submitted: date

date_required: Optional[date]    # Per schedule

review_action: ReviewAction

status: SubmittalStatus

reviewer: Optional[str]

review_date: Optional[date]

review_comments: Optional[str]

resubmittal_of: Optional[str]    # Links to prior submittal

revision: int = 0

class SubmittalStatus(str, Enum):

PENDING = 'pending'

IN_REVIEW = 'in_review'

APPROVED = 'approved'

APPROVED_AS_NOTED = 'approved_as_noted'

REVISE_RESUBMIT = 'revise_resubmit'

REJECTED = 'rejected'

FOR_INFORMATION = 'for_information'

IMPORTANT: The workflow agent monitors submittal status against the construction schedule. When a submittal required 'before_installation' is not yet approved and the installation activity is within 2 weeks of start, the agent alerts both the contractor and the reviewer.

# 4. Standards Cross-Reference Engine

The standards engine maintains a registry of all referenced standards (ASTM, AASHTO, ACI, AISC, AWS, etc.) with edition tracking, supersession chains, and cross-references to specification sections. All operations are deterministic.

## 4.1 Standard Reference Model

class StandardReference(BaseModel):

designator: str                 # 'ASTM D698'

title: str                      # 'Test Method for Lab Compaction...'

organization: str               # 'ASTM International'

current_edition: str            # '2012 (Reapproved 2021)'

status: Literal['active', 'withdrawn', 'superseded', 'historical']

superseded_by: Optional[str]    # If superseded

scope_summary: str

related_standards: List[str]    # Other standards in same family

geolab_module: Optional[str]    # Link to GeoLab test module

sections_referencing: List[str] # Spec sections that cite this

## 4.2 ASTM Standards Registry (Geotechnical)

The following ASTM standards are pre-loaded in the registry with full cross-reference data. This represents the core geotechnical testing standards that link GeoLab test modules to specification requirements.

### 4.2.1 Soil Classification Standards

| Standard | Title | GeoLab Module | Spec Sections |
| --- | --- | --- | --- |
| ASTM D2487 | Classification of Soils (USCS) | soil_classification | 31 05 13, 31 23 00 |
| ASTM D3282 | Classification of Soils (AASHTO) | soil_classification | 31 05 13, 32 11 00 |
| ASTM D2488 | Visual-Manual Soil Description | field_description | 02 30 00, 31 00 00 |
| ASTM D4318 | Liquid Limit, Plastic Limit, PI | atterberg_limits | 31 05 13, 31 23 23 |
| ASTM D6913 | Particle-Size Distribution (Sieve) | gradation | 31 05 13, 31 05 16 |
| ASTM D7928 | Particle-Size (Hydrometer) | gradation | 31 05 13 |
| ASTM D2216 | Laboratory Moisture Content | moisture_content | 31 23 00, 31 23 23 |
| ASTM D854 | Specific Gravity of Soils | specific_gravity | 31 05 13 |
| ASTM D4427 | Classification of Peat | organics | 31 05 13 |

### 4.2.2 Compaction & Density Standards

| Standard | Title | GeoLab Module | Spec Sections |
| --- | --- | --- | --- |
| ASTM D698 | Standard Proctor Compaction | proctor_standard | 31 23 00, 31 23 23 |
| ASTM D1557 | Modified Proctor Compaction | proctor_modified | 31 23 00, 32 11 00 |
| ASTM D6938 | In-Place Density (Nuclear) | field_density | 31 23 00, 31 23 23 |
| ASTM D1556 | In-Place Density (Sand Cone) | field_density | 31 23 00 |
| ASTM D2167 | In-Place Density (Rubber Balloon) | field_density | 31 23 00 |
| ASTM D4253 | Max Index Density (Vibratory) | relative_density | 31 23 00 |
| ASTM D4254 | Min Index Density | relative_density | 31 23 00 |
| ASTM D7382 | In-Place Density (Heavy Compaction) | field_density | 31 23 00 |

### 4.2.3 Strength Testing Standards

| Standard | Title | GeoLab Module | Spec Sections |
| --- | --- | --- | --- |
| ASTM D2166 | Unconfined Compressive Strength | ucs | 31 32 00, 31 63 00 |
| ASTM D2850 | Unconsolidated Undrained Triaxial | triaxial_uu | 31 40 00, 31 50 00 |
| ASTM D4767 | Consolidated Undrained Triaxial | triaxial_cu | 31 40 00, 31 50 00 |
| ASTM D7181 | Consolidated Drained Triaxial | triaxial_cd | 31 40 00, 31 50 00 |
| ASTM D3080 | Direct Shear | direct_shear | 31 40 00, 31 50 00 |
| ASTM D1883 | California Bearing Ratio (CBR) | cbr | 31 05 16, 32 11 00 |
| ASTM D5731 | Point Load Index | point_load | 31 23 17, 31 30 00 |
| ASTM D7012 | Rock Compressive Strength (UCS) | rock_ucs | 31 23 17, 31 33 00 |
| ASTM D3967 | Brazilian Tensile Strength | brazilian_tensile | 31 33 00 |

### 4.2.4 Consolidation & Permeability Standards

| Standard | Title | GeoLab Module | Spec Sections |
| --- | --- | --- | --- |
| ASTM D2435 | One-Dimensional Consolidation | consolidation | 31 23 00, 35 20 00 |
| ASTM D4186 | Constant Rate of Strain Consolidation | crs_consolidation | 31 23 00, 35 20 00 |
| ASTM D2434 | Permeability (Constant Head) | permeability | 31 23 19, 35 51 00 |
| ASTM D5084 | Permeability (Flexible Wall) | permeability | 31 23 19, 35 20 00 |
| ASTM D5856 | Permeability (Rigid Wall, Compacted) | permeability | 35 20 00 |
| ASTM D4186 | CRS Consolidation | crs_consolidation | 31 23 00 |

### 4.2.5 Concrete Testing Standards

| Standard | Title | GeoLab Module | Spec Sections |
| --- | --- | --- | --- |
| ASTM C39 | Compressive Strength of Cylinders | concrete_compression | 03 30 00, 03 31 00 |
| ASTM C143 | Slump of Hydraulic Cement Concrete | concrete_slump | 03 30 00 |
| ASTM C231 | Air Content (Pressure Method) | concrete_air | 03 30 00 |
| ASTM C1064 | Temperature of Freshly Mixed Concrete | concrete_temp | 03 30 00 |
| ASTM C138 | Unit Weight and Yield | concrete_unit_weight | 03 30 00 |
| ASTM C31 | Making and Curing Cylinders in Field | concrete_cylinders | 03 30 00 |
| ASTM C78 | Flexural Strength of Concrete | concrete_flexure | 32 13 00 |
| ASTM C496 | Splitting Tensile Strength | concrete_tensile | 03 31 00 |
| ASTM C42 | Drilled Cores and Sawed Beams | concrete_cores | 03 31 00 |

## 4.3 Standard Validation Rules

The engine performs deterministic validation checks on all standard references:

| Rule ID | Check | Action on Failure |
| --- | --- | --- |
| STD-001 | Referenced standard exists in registry | Error: unknown standard |
| STD-002 | Referenced edition is current | Warning: superseded edition |
| STD-003 | Standard has not been withdrawn | Error: withdrawn standard |
| STD-004 | Standard scope matches usage context | Warning: possible misapplication |
| STD-005 | Test method matches GeoLab module capability | Warning: unsupported test type |
| STD-006 | No circular cross-references between sections | Error: circular dependency |
| STD-007 | All cross-referenced sections exist in project spec | Warning: unresolved cross-ref |
| STD-008 | Referenced standard year matches spec edition year | Info: edition mismatch |

NOTE: Standard edition tracking is critical for government contracts. Many agencies require specific editions (e.g., 'ASTM D698-12e2' not just 'ASTM D698'). The engine validates that edition years referenced in specifications match the agency's adopted edition list.

# 5. Specification Compliance Engine

The compliance engine verifies that construction activities, submittals, and test results meet specification requirements. Operations are deterministic where requirements are quantifiable, with AI augmentation for natural-language interpretation.

## 5.1 Compliance Check Types

| Check Type | Method | Description | Example |
| --- | --- | --- | --- |
| Quantitative | Deterministic | Compare numeric value against min/max/range | Compressive strength >= 4,000 psi at 28 days |
| Categorical | Deterministic | Verify value is within allowed set | Cement Type in {I, I/II, II, V} |
| Frequency | Deterministic | Verify testing frequency meets requirement | 1 density test per 500 CY placed |
| Procedural | Deterministic | Verify required steps were performed in order | Pre-installation meeting held before work |
| Completeness | Deterministic | All required submittals/tests present | Mix design submitted before ordering |
| Conflict | AI-Augmented | Detect contradictions across sections | Section A requires Type V, Section B allows Type I/II |
| Equivalence | AI-Augmented | Assess if substitute product meets intent | Proposed equal evaluation |
| Narrative | AI-Augmented | Interpret specification intent from language | "Compacted to a firm, unyielding surface" |

## 5.2 Quantitative Compliance Model

class ComplianceCheck(BaseModel):

check_id: str

spec_section: str

spec_paragraph: str

requirement: PropertyRequirement

test_result: TestResult

@computed_field

@property

def status(self) -> ComplianceStatus:

value = self.test_result.value

req = self.requirement

if req.minimum and value < req.minimum:

return ComplianceStatus.FAIL

if req.maximum and value > req.maximum:

return ComplianceStatus.FAIL

if req.minimum and value < req.minimum * Decimal('1.05'):

return ComplianceStatus.MARGINAL  # Within 5% of limit

return ComplianceStatus.PASS

class ComplianceStatus(str, Enum):

PASS = 'pass'

MARGINAL = 'marginal'           # Passes but near limit

FAIL = 'fail'

INSUFFICIENT_DATA = 'insufficient_data'

NOT_TESTED = 'not_tested'

## 5.3 Specification Completeness Scoring

SP-004: Specification Completeness Score

Completeness = (Present Sections / Required Sections) × 100

The engine evaluates specification completeness at multiple levels:

| Level | What Is Checked | Weight |
| --- | --- | --- |
| Division Coverage | Are all required divisions present for project type? | 25% |
| Section Coverage | Are all required sections present within each division? | 25% |
| Content Completeness | Does each section have all 3 parts populated? | 20% |
| Standard References | Are all cited standards valid and current? | 15% |
| Submittal Requirements | Are submittal requirements defined for all products? | 15% |

WARNING: A completeness score below 85% triggers an agent warning. Below 70% blocks estimate finalization—an incomplete specification means the cost estimate is unreliable because testing, QC, and material requirements are undefined.

## 5.4 Conflict Detection (AI-Augmented)

SP-005: Specification Conflict Detection

The conflict detection engine identifies contradictory requirements across specification sections. This uses semantic comparison to find requirements that address the same topic but specify different values or criteria.

| Conflict Type | Example | Detection Method | Severity |
| --- | --- | --- | --- |
| Direct Contradiction | Sec A: 95% Proctor; Sec B: 98% Proctor for same material | Value comparison on shared parameter | Critical |
| Standard Conflict | Sec A cites ASTM D698; Sec B cites ASTM D1557 for same test | Standard registry lookup | High |
| Material Mismatch | Sec A: Type V cement; Sec B: Type I/II acceptable | Material property comparison | High |
| Tolerance Conflict | Sec A: ±0.1 ft; Sec B: ±0.04 ft for same surface | Tolerance range comparison | Moderate |
| Ambiguous Cross-Ref | "Per Division 31" without specific section | Cross-ref resolution failure | Low |
| Orphaned Requirement | Testing required but no acceptance criterion defined | Completeness check | Moderate |

class ConflictDetectionResult(BaseModel):

conflicts: List[SpecConflict]

warnings: List[SpecWarning]

confidence: float              # AI confidence in findings

class SpecConflict(BaseModel):

conflict_id: str

severity: Literal['critical', 'high', 'moderate', 'low']

section_a: str                 # First section

paragraph_a: str

requirement_a: str             # The conflicting text

section_b: str                 # Second section

paragraph_b: str

requirement_b: str

conflict_type: str

description: str               # Human-readable explanation

suggested_resolution: Optional[str]  # AI-suggested fix

# 6. Testing & Inspection Integration

GEOLAB BRIDGE

Specification testing requirements are the contractual link between lab testing (GeoLab) and field construction acceptance. This section defines how spec requirements drive testing programs and cost.

## 6.1 Testing Frequency Matrix

The testing frequency matrix maps specification requirements to test frequencies, generating both testing schedules and cost line items. This is fully deterministic—frequency is calculated from specified volumes and the spec-defined testing interval.

| Spec Section | Test | ASTM Method | Frequency | Cost/Test |
| --- | --- | --- | --- | --- |
| 31 23 00 | Field Density | D6938 | 1 per 500 CY fill placed | $35–$75 |
| 31 23 00 | Moisture Content | D2216 | 1 per 500 CY (with density) | $15–$30 |
| 31 23 00 | Proctor Compaction | D698/D1557 | 1 per soil type + 1 per 5,000 CY | $150–$300 |
| 31 23 23 | Backfill Density | D6938 | 1 per 100 LF trench | $35–$75 |
| 31 05 16 | Aggregate Gradation | C136/D6913 | 1 per 2,000 tons or 1/source | $75–$150 |
| 31 05 16 | Sand Equivalent | D2419 | 1 per 2,000 tons | $40–$80 |
| 31 32 00 | Stabilized Soil UCS | D2166 | 1 per 1,000 CY treated | $75–$150 |
| 03 30 00 | Concrete Cylinders (set of 4) | C31/C39 | 1 set per 50 CY or 1/day | $80–$160 |
| 03 30 00 | Slump Test | C143 | Each truck (min) | $0 (field) |
| 03 30 00 | Air Content | C231 | Each truck (min) | $0 (field) |
| 03 30 00 | Concrete Temperature | C1064 | Each truck | $0 (field) |
| 32 11 00 | Base Course Density | D6938 | 1 per 500 SY placed | $35–$75 |
| 32 12 00 | HMA Core Density | D6927 | 1 per 500 tons | $75–$150 |

## 6.2 Testing Cost Generation Equations

SP-001: Testing Frequency Cost

Test Count = ceiling(Work Volume / Test Interval)

Testing Cost = Test Count × Unit Test Cost

Worked example for a project with 25,000 CY of structural fill:

| Test | Interval | Count | Unit Cost | Extended |
| --- | --- | --- | --- | --- |
| Field Density | 1 per 500 CY | 50 | $55 | $2,750 |
| Moisture Content | 1 per 500 CY | 50 | $22 | $1,100 |
| Proctor (2 soil types) | 1/type + 1/5,000 CY | 7 | $225 | $1,575 |
| Gradation (verification) | 1 per 5,000 CY | 5 | $110 | $550 |
| Total Field Testing (fill only) |  | 112 |  | $5,975 |

IMPORTANT: This testing cost is auto-generated and flows directly into the Cost Estimating domain as a QC/Testing indirect cost line item. When earthwork volume changes (e.g., design revision), testing costs update automatically.

## 6.3 Submittal Processing Time Equation

SP-002: Submittal Processing Duration

Processing Days = Submittal Count × Avg Review Cycle × Resubmittal Factor

| Parameter | Typical Value | Source |
| --- | --- | --- |
| Review Cycle (standard) | 14–21 calendar days | Contract requirement (01 33 00) |
| Review Cycle (expedited) | 7–10 calendar days | Fast-track provision |
| Resubmittal Factor | 1.15–1.30 | 15–30% of submittals require resubmission |
| Concurrent review capacity | 5–10 submittals | Design team bandwidth |
| Critical path submittals | Identified per schedule | Long-lead items, structural |

Schedule Impact: The agent integrates submittal processing time into the CPM schedule. If the calculated submittal processing time exceeds the available float before the related construction activity, the agent flags a potential delay and recommends expedited review or early submittal submission.

## 6.4 GeoLab Test Result → Spec Compliance Flow

The complete flow from laboratory testing through specification compliance:

- Step 1 — Sample Collection: Field sample taken per spec frequency (e.g., 1 per 500 CY). Sample ID logged in GeoLab chain-of-custody.

- Step 2 — Lab Testing: GeoLab performs test per ASTM method referenced in spec. Results computed deterministically using GeoLab calculation engine.

- Step 3 — Result Validation: GeoLab validates result against method requirements (e.g., specimen dimensions, strain rate). Flags non-compliant testing procedures.

- Step 4 — Compliance Check: ENGR-KB specs engine compares result against acceptance criterion from the specification (e.g., >= 95% of max dry density).

- Step 5 — Status Update: Result classified as PASS / MARGINAL / FAIL. Marginal results (within 5% of limit) flagged for engineering review.

- Step 6 — Agent Action: PASS: log and continue. MARGINAL: notify engineer. FAIL: trigger NCR workflow, halt affected work, require corrective action plan.

# 7. Specification-Cost Integration

Specifications drive costs in ways beyond just testing. Material grade requirements, installation method constraints, and QA/QC provisions all impact the cost estimate. This section documents the deterministic linkages between spec requirements and cost line items.

## 7.1 Material Specification Cost Impacts

| Spec Requirement | Cost Impact | Typical Premium | How Tracked |
| --- | --- | --- | --- |
| Type V cement (sulfate resistant) | vs. Type I/II | +10–20% material | Material grade field in unit cost |
| Epoxy-coated rebar | vs. uncoated | +30–50% material | Material specification field |
| Stainless steel connections | vs. galvanized | +200–400% material | Material specification field |
| Select granular backfill | vs. common backfill | +50–100% material | Material source requirement |
| Low-permeability clay liner | vs. standard compaction | +20–40% placement | Method specification |
| Hot weather concrete (admixtures) | vs. standard mix | +5–15% material | Mix design requirement |
| Self-consolidating concrete | vs. conventional | +15–30% material | Mix design requirement |
| Geomembrane liner (HDPE 60 mil) | vs. 40 mil | +40–60% material | Thickness specification |

## 7.2 Spec-Driven Quantity Generation

SP-QTY-001: Specification-Generated Quantities

Certain specification requirements automatically generate quantity line items in the cost estimate:

| Spec Requirement | Generated Line Item | Formula |
| --- | --- | --- |
| Compaction test per 500 CY | Field density tests | ceil(Fill Vol / 500) |
| Concrete cylinders per 50 CY | Cylinder test sets | ceil(Conc Vol / 50) × 4 cyl/set |
| Gradation test per 2,000 tons | Gradation tests | ceil(Tonnage / 2000) |
| Full-time inspection | Inspector person-days | Activity duration (working days) |
| Survey per 1,000 LF | Survey setups | ceil(Length / 1000) |
| Erosion control inspection weekly | Inspections | Duration (weeks) |
| Concrete curing compound | Cure compound (gal) | Exposed area (SF) × coverage rate |
| Form release agent | Release agent (gal) | Form area (SFCA) × coverage rate |

## 7.3 Specification Revision Cost Impact

When specifications change during a project, the system calculates the cost impact of the revision. This feeds directly into the change order processing workflow.

class SpecRevisionImpact(BaseModel):

spec_section: str

revision_from: int

revision_to: int

changes: List[SpecChange]

cost_impact: Decimal             # Net cost change

schedule_impact_days: int        # Net schedule change

affected_submittals: List[str]   # Submittals needing update

class SpecChange(BaseModel):

change_type: Literal[

'material_upgrade',          # More expensive material

'material_downgrade',        # Less expensive material

'testing_frequency_increase', # More testing required

'testing_frequency_decrease',

'tolerance_tighter',          # Tighter = more labor/rework

'tolerance_looser',

'method_change',              # Different construction method

'new_requirement',            # Added requirement

'removed_requirement',

]

description: str

old_value: Optional[str]

new_value: Optional[str]

estimated_cost_impact: Decimal

affected_line_items: List[str]   # Cost estimate line item IDs

IMPORTANT: The agent monitors specification revisions and automatically estimates cost/schedule impacts. For critical changes (material upgrades, tighter tolerances), the agent generates a draft change order with cost backup for review before routing to the approver.

## 7.4 Specification Equations Catalog

| ID | Name | Formula | Type |
| --- | --- | --- | --- |
| SP-001 | Testing Frequency Cost | ceil(Volume/Interval) × Unit Test Cost | Deterministic |
| SP-002 | Submittal Processing Time | Count × Cycle × Resub Factor | Parametric |
| SP-003 | Cross-Reference Graph | DAG of section dependencies | Graph traversal |
| SP-004 | Completeness Score | (Present/Required) × 100, weighted | Deterministic |
| SP-005 | Conflict Detection | Semantic similarity on requirement pairs | AI-Augmented |
| SP-QTY-001 | Spec-Generated Quantities | ceil(Work Volume / Spec Interval) | Deterministic |
| SP-REV-001 | Revision Cost Impact | Σ(Change × Unit Cost Delta × Affected Qty) | Deterministic |
| SP-STD-001 | Standard Validity Check | Edition vs. registry current | Deterministic |
| SP-SUB-001 | Submittal Status Score | (Approved / Required) by activity | Deterministic |
| SP-CMP-001 | Quantitative Compliance | Test Value vs. Spec Limit | Deterministic |

## 7.5 Reference Data Summary

| Data Table | Records | Source | Update |
| --- | --- | --- | --- |
| MasterFormat Division Index | 49 divisions | CSI 2018 | As published |
| MasterFormat Section Index | ~1,500 sections | CSI 2018 | As published |
| ASTM Standard Registry (geotech) | ~80 standards | ASTM catalog | Annual |
| ASTM Standard Registry (concrete) | ~50 standards | ASTM catalog | Annual |
| AASHTO Standard Registry | ~40 standards | AASHTO catalog | Annual |
| ACI Standard Registry | ~30 standards | ACI catalog | Annual |
| Testing Frequency Defaults | ~40 test types | Agency guide specs | User calibration |
| Testing Unit Costs | ~40 test types | Lab pricing, public data | Annual |
| Guide Spec Templates | ~60 sections | USACE, state DOTs | User customization |
| Submittal Type Defaults | ~20 types per section | Industry practice | Static |
| Material Property Requirements | ~100 materials | ASTM/ACI/AASHTO | Per standard update |