ENGR-KB

Engineering Knowledge Base

Project Management

CPM Scheduling, Earned Value, Risk Analysis, Change Orders & Resource Management

v1.0  |  February 2026

ENGR-KB Document Series  |  Document 4 of 6

DRAFT — INTERNAL USE ONLY

# Table of Contents

# 1. Project Management Domain Overview

The Project Management domain provides deterministic engines for scheduling (CPM/PERT), Earned Value Management (EVM), risk analysis (Monte Carlo), resource management, and change order processing. These engines integrate tightly with Cost Estimating (cost-loaded schedules, EVM tracking) and Specifications (submittal timelines, testing milestones) to form the operational backbone of the workflow automation agent.

Core Design Principle: Schedule and cost performance metrics are computed deterministically from validated algorithms. AI augmentation is applied only where human judgment is needed: narrative report generation, root cause analysis suggestions, and trend interpretation. The agent never autonomously adjusts a baseline schedule or budget—it recommends, alerts, and routes for human decision.

## 1.1 Scope of Coverage

| Capability | Method | Type | ANSI/PMI Alignment |
| --- | --- | --- | --- |
| Critical Path Method | Forward/backward pass, float calc | Deterministic | PMBOK 6th/7th, AACE RP 49R |
| PERT Duration Analysis | Three-point estimate, beta distribution | Probabilistic | PMBOK, AACE RP 41R |
| Earned Value Management | All 32 ANSI/EIA-748 criteria | Deterministic | EIA-748-D |
| Monte Carlo Schedule Risk | N-iteration probabilistic simulation | Probabilistic | AACE RP 57R-09 |
| Resource Leveling | Heuristic + constraint-based | Algorithmic | PMBOK |
| Cash Flow Projection | Cost-loaded schedule, S-curve | Deterministic | AACE RP 29R-03 |
| Change Order Processing | Cost + schedule impact analysis | Det. + AI narrative | FAR/contract terms |
| Risk Register Management | P×I matrix, EMV, risk response | Deterministic | PMBOK, ISO 31000 |
| Progress Measurement | % complete methods, milestones | Deterministic | AACE RP 10S-90 |
| Schedule Delay Analysis | As-planned vs. as-built, TIA, windows | Deterministic | AACE RP 29R-03 |

## 1.2 Schedule Data Architecture

The scheduling engine operates on a directed acyclic graph (DAG) of activities connected by dependency relationships. This is the standard CPM network model used by all major scheduling software.

class Schedule(BaseModel):

"""Complete project schedule (CPM network)."""

schedule_id: str

project_id: str

project_name: str

data_date: date                  # Status/progress date

project_start: date

project_finish: Optional[date]   # Calculated

activities: List[Activity]

relationships: List[Relationship]

calendars: List[Calendar]

wbs: List[WBSNode]

# Baselines

baseline_finish: Optional[date]

baseline_cost: Optional[Decimal]

# Calculated outputs

critical_path: List[str]         # Activity IDs on CP

project_duration: int            # Working days

total_float_histogram: Dict[int, int]  # float days -> activity count

# 2. CPM Scheduling Engine

The Critical Path Method engine computes early/late dates, float values, and the critical path through the network. The implementation follows the standard forward/backward pass algorithm with support for all four relationship types, lags, constraints, and multiple calendars.

## 2.1 Activity Model

class Activity(BaseModel):

activity_id: str

name: str

wbs_code: str

duration: int                    # Working days (original)

remaining_duration: int          # Working days remaining

percent_complete: float          # 0.0-1.0

calendar_id: str

# Constraints

constraint_type: Optional[ConstraintType]

constraint_date: Optional[date]

# Cost loading

budget_cost: Decimal = Decimal('0')

actual_cost: Decimal = Decimal('0')

cost_account: Optional[str]      # Links to estimate WBS

# Resource assignments

resources: List[ResourceAssignment]

# Calculated fields (populated by CPM engine)

early_start: Optional[date]

early_finish: Optional[date]

late_start: Optional[date]

late_finish: Optional[date]

total_float: Optional[int]

free_float: Optional[int]

is_critical: bool = False

# Links to other domains

spec_sections: List[str]         # Applicable specifications

required_submittals: List[str]   # Must be approved before start

class ConstraintType(str, Enum):

AS_SOON_AS_POSSIBLE = 'asap'     # Default

AS_LATE_AS_POSSIBLE = 'alap'

START_NO_EARLIER_THAN = 'snet'

START_NO_LATER_THAN = 'snlt'

FINISH_NO_EARLIER_THAN = 'fnet'

FINISH_NO_LATER_THAN = 'fnlt'

MUST_START_ON = 'mso'

MUST_FINISH_ON = 'mfo'

## 2.2 Relationship Types

class Relationship(BaseModel):

predecessor_id: str

successor_id: str

relationship_type: RelationType

lag: int = 0                     # Working days (+ or -)

class RelationType(str, Enum):

FINISH_TO_START = 'FS'           # Most common (default)

START_TO_START = 'SS'

FINISH_TO_FINISH = 'FF'

START_TO_FINISH = 'SF'           # Rare

| Type | Meaning | Formula | Common Use |
| --- | --- | --- | --- |
| FS | Successor starts after predecessor finishes | ES_j = EF_i + lag | Sequential activities (90% of relationships) |
| SS | Successor starts after predecessor starts | ES_j = ES_i + lag | Parallel activities with offset start |
| FF | Successor finishes after predecessor finishes | EF_j = EF_i + lag | Activities that must end together |
| SF | Successor finishes after predecessor starts | EF_j = ES_i + lag | Very rare; just-in-time delivery |

## 2.3 CPM Core Equations

The CPM algorithm consists of a forward pass (computing early dates) and a backward pass (computing late dates). Float is derived from the difference between early and late dates.

### 2.3.1 Forward Pass

PM-001: Early Start

ES_j = max(EF_i + lag_ij) for all predecessors i of activity j

PM-002: Early Finish

EF_j = ES_j + Duration_j - 1  (working days on calendar)

For FS relationships: ES_successor = EF_predecessor + lag + 1

For SS relationships: ES_successor = ES_predecessor + lag

For FF relationships: EF_successor = EF_predecessor + lag

For SF relationships: EF_successor = ES_predecessor + lag

### 2.3.2 Backward Pass

PM-003: Late Finish

LF_j = min(LS_k - lag_jk) for all successors k of activity j

PM-004: Late Start

LS_j = LF_j - Duration_j + 1

### 2.3.3 Float Calculations

PM-005: Total Float

TF_j = LS_j - ES_j = LF_j - EF_j

PM-006: Free Float

FF_j = min(ES_k - lag_jk) - EF_j for all FS successors k

PM-007: Critical Path Identification

Critical Path = {activities where TF = 0}

| Float Type | Meaning | Agent Use |
| --- | --- | --- |
| Total Float = 0 | Activity is critical—any delay extends project | Highest priority monitoring |
| Total Float 1–5 | Near-critical—small delays could make it critical | Watch list, early warning |
| Total Float 6–20 | Moderate flexibility | Standard monitoring |
| Total Float > 20 | Significant flexibility | Low-priority monitoring |
| Free Float = 0 | Any delay affects immediate successor(s) | Coordination trigger |
| Free Float > 0 | Can delay without affecting any successor | Flexibility for resource leveling |

## 2.4 CPM Engine Implementation

class CPMEngine:

def __init__(self, schedule: Schedule):

self.schedule = schedule

self._build_graph()

def _build_graph(self):

"""Build adjacency lists from relationships."""

self.successors = defaultdict(list)  # id -> [(id, type, lag)]

self.predecessors = defaultdict(list)

for rel in self.schedule.relationships:

self.successors[rel.predecessor_id].append(

(rel.successor_id, rel.relationship_type, rel.lag))

self.predecessors[rel.successor_id].append(

(rel.predecessor_id, rel.relationship_type, rel.lag))

def forward_pass(self):

"""Compute ES and EF for all activities (topological order)."""

order = self._topological_sort()

for act_id in order:

act = self._get_activity(act_id)

if not self.predecessors[act_id]:  # Start activity

act.early_start = self.schedule.project_start

else:

es_candidates = []

for pred_id, rel_type, lag in self.predecessors[act_id]:

pred = self._get_activity(pred_id)

es_candidates.append(

self._calc_es(pred, rel_type, lag, act))

act.early_start = max(es_candidates)

act.early_finish = self._add_workdays(

act.early_start, act.duration, act.calendar_id)

def backward_pass(self):

"""Compute LS and LF (reverse topological order)."""

order = list(reversed(self._topological_sort()))

# Set project finish from latest EF

project_ef = max(a.early_finish for a in self.schedule.activities)

for act_id in order:

act = self._get_activity(act_id)

if not self.successors[act_id]:  # Finish activity

act.late_finish = project_ef

else:

lf_candidates = []

for succ_id, rel_type, lag in self.successors[act_id]:

succ = self._get_activity(succ_id)

lf_candidates.append(

self._calc_lf(succ, rel_type, lag, act))

act.late_finish = min(lf_candidates)

act.late_start = self._sub_workdays(

act.late_finish, act.duration, act.calendar_id)

act.total_float = self._workday_diff(

act.early_start, act.late_start)

act.is_critical = (act.total_float == 0)

## 2.5 Calendar Model

Calendars define working days and hours. Different activities can use different calendars (e.g., concrete work uses a 5-day calendar; shift work uses 7-day).

class Calendar(BaseModel):

calendar_id: str

name: str

workdays: List[int]             # 0=Mon ... 6=Sun

hours_per_day: float

holidays: List[date]

weather_days: WeatherAllowance   # Expected lost weather days

class WeatherAllowance(BaseModel):

"""Monthly weather day allowance based on historical data."""

monthly_lost_days: Dict[int, float]  # month (1-12) -> avg lost days

basis: str                       # 'NOAA 30-yr avg, Denver metro'

| Calendar Type | Work Days | Typical Use | Weather Impact |
| --- | --- | --- | --- |
| 5-Day Standard | Mon-Fri | General construction, office | Full weather impact |
| 6-Day Extended | Mon-Sat | Heavy civil, earthwork | Full weather impact |
| 7-Day Continuous | All days | Concrete curing, dewatering | Partial (crew still works) |
| Shift Calendar | Custom | Tunnel, 24-hr operations | Reduced (underground) |
| Weather-Adjusted | Mon-Fri minus lost days | Outdoor work, regional | Built into calendar |

## 2.6 Duration Estimation Methods

Activity durations are derived from production rates (Construction Engineering domain) and quantities (Cost Estimating domain). The scheduling engine supports multiple duration estimation methods.

PM-008: Production-Based Duration

Duration = Quantity / (Daily Production × Crew Count × Weather Factor × Efficiency)

PM-009: PERT Three-Point Duration

Expected = (Optimistic + 4×Most_Likely + Pessimistic) / 6

Std Dev = (Pessimistic - Optimistic) / 6

PM-010: Learning Curve Duration (Repetitive Work)

T_n = T_1 × n^(log(learning_rate) / log(2))

| Activity Type | Learning Rate | Example |
| --- | --- | --- |
| Formwork (repetitive) | 85–90% | Each floor/bay faster than previous |
| Pile driving | 90–95% | Crew improves setup/driving rhythm |
| Pipe installation | 88–92% | Crew speeds up on long runs |
| Tunnel lining (segmental) | 80–88% | Significant learning on ring erection |
| Precast erection | 85–90% | Crane/rigging crew optimization |

IMPORTANT: Learning curve durations compound with production-based estimates from the Construction Engineering domain. For a 200-pile project with T_1 = 3 hours and 90% learning rate, the average time per pile drops to approximately 2.1 hours by pile 200, reducing total duration by ~30% vs. using the initial rate for all piles.

# 3. Earned Value Management (EVM)

The EVM engine implements all metrics defined in the ANSI/EIA-748 Earned Value Management Systems standard. EVM integrates cost and schedule performance into a single measurement framework, providing the primary data feed for the workflow automation agent’s project health monitoring.

## 3.1 Core EVM Metrics

| ID | Metric | Full Name | Formula | Interpretation |
| --- | --- | --- | --- | --- |
| PM-020 | BAC | Budget at Completion | Total baseline budget | What we plan to spend |
| PM-021 | PV | Planned Value (BCWS) | Planned % × BAC | What should we have spent |
| PM-022 | EV | Earned Value (BCWP) | Actual % × BAC | Value of work done |
| PM-023 | AC | Actual Cost (ACWP) | Sum of actual costs | What we actually spent |
| PM-024 | SV | Schedule Variance | EV - PV | + ahead, - behind |
| PM-025 | CV | Cost Variance | EV - AC | + under, - over budget |
| PM-026 | SPI | Schedule Perf. Index | EV / PV | >1 ahead, <1 behind |
| PM-027 | CPI | Cost Perf. Index | EV / AC | >1 under, <1 over |
| PM-028 | SV% | Schedule Var. % | SV / PV × 100 | % schedule variance |
| PM-029 | CV% | Cost Var. % | CV / EV × 100 | % cost variance |

## 3.2 Forecasting Metrics

| ID | Metric | Formula | When to Use |
| --- | --- | --- | --- |
| PM-030 | EAC (CPI) | BAC / CPI | Current cost trend will continue |
| PM-031 | EAC (CPI×SPI) | AC + (BAC-EV)/(CPI×SPI) | Both cost and schedule affect future |
| PM-032 | EAC (new est.) | AC + ETC (bottom-up) | Prior assumptions no longer valid |
| PM-033 | EAC (budget) | AC + (BAC - EV) | Variance was atypical, won't recur |
| PM-034 | ETC | EAC - AC | Remaining cost to complete |
| PM-035 | VAC | BAC - EAC | Expected overrun(-) or underrun(+) |
| PM-036 | TCPI (BAC) | (BAC - EV) / (BAC - AC) | Performance needed to hit BAC |
| PM-037 | TCPI (EAC) | (BAC - EV) / (EAC - AC) | Performance needed to hit EAC |

NOTE: TCPI > 1.0 means the team must perform better than historical to meet the target. TCPI > 1.10 is generally considered unrealistic without scope reduction or additional funding. The agent flags TCPI(BAC) > 1.10 as requiring management action.

## 3.3 EVM Data Model

class EVMSnapshot(BaseModel):

"""EVM metrics at a point in time."""

project_id: str

data_date: date

period: str                      # 'monthly', 'weekly'

# Baseline

bac: Decimal

# Measured

pv: Decimal

ev: Decimal

ac: Decimal

# Variances (computed)

@computed_field

@property

def sv(self) -> Decimal: return self.ev - self.pv

@computed_field

@property

def cv(self) -> Decimal: return self.ev - self.ac

@computed_field

@property

def spi(self) -> Decimal:

return self.ev / self.pv if self.pv else Decimal('0')

@computed_field

@property

def cpi(self) -> Decimal:

return self.ev / self.ac if self.ac else Decimal('0')

# Forecasts

@computed_field

@property

def eac_cpi(self) -> Decimal:

return self.bac / self.cpi if self.cpi else self.bac

@computed_field

@property

def eac_composite(self) -> Decimal:

denom = self.cpi * self.spi

if not denom: return self.bac

return self.ac + (self.bac - self.ev) / denom

@computed_field

@property

def tcpi_bac(self) -> Decimal:

denom = self.bac - self.ac

if not denom: return Decimal('0')

return (self.bac - self.ev) / denom

@computed_field

@property

def vac(self) -> Decimal:

return self.bac - self.eac_cpi

## 3.4 Percent Complete Methods

Earned Value depends on accurate percent-complete measurement. The engine supports multiple methods, enforced by activity type to prevent gaming.

| Method | Description | Best For | Risk of Manipulation |
| --- | --- | --- | --- |
| Units Complete | EV = (units done / total units) × BAC | Repetitive production (earthwork, pipe) | Low |
| Weighted Milestones | EV = sum of milestone values achieved | Phased work, design activities | Low |
| 0/50/100 | 0% at start, 50% when started, 100% done | Short activities (<2 weeks) | Very Low |
| 0/100 | 0% until complete, then 100% | Very short activities (<1 week) | None |
| Level of Effort | EV = PV (time-based) | Support activities, management | N/A (always on plan) |
| Supervisor Estimate | Supervisor assigns % complete | Complex one-off activities | High |
| Cost Ratio | EV = (AC / EAC) × BAC | Subcontracted work | Moderate |

IMPORTANT: The agent enforces method assignment by activity type. Earthwork activities must use 'Units Complete' (CY placed). Concrete activities use 'Units Complete' (CY placed) or 'Weighted Milestones' (form/pour/strip). 'Supervisor Estimate' is only permitted with monthly variance explanations.

## 3.5 EVM Alert Thresholds & Agent Actions

The workflow agent continuously monitors EVM metrics against configurable thresholds. Each threshold triggers specific automated actions.

| Condition | Level | Agent Action | Escalation |
| --- | --- | --- | --- |
| CPI or SPI in [0.90, 0.95) | Watch | Log trend, no notification | None |
| CPI or SPI in [0.85, 0.90) | Warning | Notify PM, request variance explanation | PM |
| CPI or SPI in [0.80, 0.85) | Alert | Require corrective action plan within 5 days | PM + Program Mgr |
| CPI or SPI < 0.80 | Critical | Escalate, require recovery plan, EAC reforecast | Senior Management |
| CPI and SPI both < 0.85 | Critical | Immediate EAC reforecast + schedule rebaseline request | Senior Management |
| TCPI(BAC) > 1.10 | Alert | Flag as likely unrecoverable, recommend management reserve | PM + Program Mgr |
| TCPI(BAC) > 1.20 | Critical | Recommend scope reduction or budget increase | Senior Management |
| VAC < -10% of BAC | Critical | Require management reserve assessment | Senior Management |
| SPI < 0.90 for 3 consecutive periods | Alert | Trend analysis, recommend schedule recovery | PM + Program Mgr |
| CPI declining 3 consecutive periods | Warning | Trend alert even if above threshold | PM |

## 3.6 EVM Reporting Integration

The EVM engine generates standardized reports aligned with government reporting requirements (CPR Format 1-5 per DI-MGMT-81466A):

| Report | Content | Frequency | AI Augmentation |
| --- | --- | --- | --- |
| CPR Format 1 (WBS) | Cost/schedule by WBS element | Monthly | Variance narrative generation |
| CPR Format 2 (Org) | Cost/schedule by performing org | Monthly | Cross-org pattern detection |
| CPR Format 3 (Baseline) | Baseline changes log | Monthly | Scope creep trend analysis |
| CPR Format 4 (Staffing) | Labor plan vs. actual by month | Monthly | Staffing gap prediction |
| CPR Format 5 (Explanation) | Variance analysis narrative | Monthly | Root cause suggestions |
| S-Curve Chart | PV/EV/AC cumulative plot | Monthly | Trend line projection |
| IEAC Forecast | Independent EAC calculation | Monthly | EAC method recommendation |

# 4. Risk Analysis Engine

The risk engine supports qualitative assessment (probability-impact matrix), quantitative analysis (Monte Carlo simulation), and risk response tracking. Risk data feeds both schedule contingency and cost contingency calculations, creating a unified risk framework across the PM and Cost Estimating domains.

## 4.1 Risk Register Model

class RiskRegister(BaseModel):

project_id: str

risks: List[Risk]

last_review_date: date

next_review_date: date

class Risk(BaseModel):

risk_id: str

title: str

description: str

category: RiskCategory

status: Literal['identified','analyzing','mitigating','monitoring',

'occurred','closed']

# Qualitative Assessment

probability: int                 # 1-5 scale

cost_impact: int                 # 1-5 scale

schedule_impact: int             # 1-5 scale

risk_score: int                  # P x max(cost, schedule impact)

# Quantitative Assessment

probability_pct: float           # 0.0-1.0

cost_impact_value: Decimal       # $ impact if occurs

schedule_impact_days: int        # Days impact if occurs

emv_cost: Decimal                # P x cost impact

emv_schedule: float              # P x schedule impact

# Risk Response

response_strategy: Literal['avoid','mitigate','transfer','accept']

response_plan: str

response_cost: Decimal           # Cost to implement response

residual_probability: float      # After response

residual_impact: Decimal         # After response

owner: str

trigger: str                     # What indicates risk is occurring

# Schedule Links

affected_activities: List[str]   # Activity IDs affected

affected_cost_items: List[str]   # Estimate line items affected

class RiskCategory(str, Enum):

TECHNICAL = 'technical'          # Design, technology, complexity

GEOTECHNICAL = 'geotechnical'    # Subsurface, GeoLab-informed

CONSTRUCTION = 'construction'    # Methods, productivity, equipment

SCHEDULE = 'schedule'            # Delays, sequencing, weather

COST = 'cost'                    # Escalation, market, labor

REGULATORY = 'regulatory'        # Permits, environmental, safety

EXTERNAL = 'external'            # Weather, supply chain, force majeure

CONTRACTUAL = 'contractual'      # Claims, disputes, scope

## 4.2 Probability-Impact Matrix

PM-040: Risk Score Calculation

Risk Score = Probability × max(Cost Impact, Schedule Impact)

| Score Range | Risk Level | Color | Agent Response |
| --- | --- | --- | --- |
| 1–4 | Low | Green | Monitor at regular risk review |
| 5–9 | Moderate | Yellow | Active monitoring, response plan required |
| 10–15 | High | Orange | Weekly monitoring, mitigation in progress |
| 16–25 | Very High | Red | Daily monitoring, immediate escalation |

### 4.2.1 Geotechnical Risk Examples (GeoLab-Informed)

GeoLab data directly informs geotechnical risk assessment. Higher data density reduces risk probability; unexpected lab results increase it.

| Risk | GeoLab Data | Low P Trigger | High P Trigger |
| --- | --- | --- | --- |
| Unexpected rock | UCS, RQD, boring logs | Dense boring grid, consistent rock | Sparse borings, variable geology |
| High water table | Piezometer data, permeability | Multiple readings, k well-defined | Limited data, artesian potential |
| Contaminated soil | Chemical testing, Phase II ESA | Clean results, no history | Detected contamination, incomplete |
| Expansive soils | Atterberg limits, swell test | Low PI (<15), low swell | High PI (>35), high swell potential |
| Soft/compressible soils | Consolidation, vane shear | Low Cc, firm consistency | High Cc, very soft, organic |
| Slope instability | Shear strength, groundwater | High φ, low GWT | Low φ, high GWT, steep geometry |
| Unsuitable fill material | Proctor, gradation, moisture | Well within spec ranges | Marginal, high moisture, high PI |

## 4.3 Monte Carlo Schedule Simulation

PM-041: Schedule Risk Analysis via Monte Carlo

The Monte Carlo engine runs N iterations of the CPM calculation, each time sampling activity durations from defined probability distributions. The output is a probability distribution of project completion dates and the criticality index (% of iterations each activity appears on the critical path).

class ScheduleMonteCarloConfig(BaseModel):

iterations: int = 10000

seed: Optional[int]

confidence_levels: List[float] = [0.50, 0.80, 0.85, 0.90, 0.95]

# Duration distributions per activity

activity_distributions: List[ActivityDistribution]

# Risk events (discrete events that may or may not occur)

risk_events: List[RiskEvent]

# Correlation

correlation_groups: List[CorrelationGroup]

class ActivityDistribution(BaseModel):

activity_id: str

distribution: Literal['triangular', 'pert', 'beta', 'uniform']

optimistic: int                  # Days (minimum duration)

most_likely: int                 # Days (expected duration)

pessimistic: int                 # Days (maximum duration)

class RiskEvent(BaseModel):

risk_id: str                     # Links to risk register

probability: float

affected_activities: List[str]

duration_impact: int             # Additional days if event occurs

cost_impact: Decimal

class ScheduleSimResult(BaseModel):

iterations_run: int

convergence: bool

deterministic_finish: date       # CPM calculated finish

p50_finish: date

p80_finish: date

p85_finish: date

p90_finish: date

p95_finish: date

schedule_contingency_p80: int    # Days beyond deterministic

schedule_contingency_p90: int

criticality_index: Dict[str, float]  # activity -> % time on CP

sensitivity: Dict[str, float]    # activity -> duration correlation

risk_event_frequency: Dict[str, float]  # risk -> % iterations triggered

IMPORTANT: A common finding: the deterministic CPM finish date typically corresponds to P20-P30 probability—meaning there's only a 20-30% chance of finishing on or before the CPM date. Most projects need P80 schedule contingency (typically 10-25% additional duration) to achieve reasonable confidence.

## 4.4 Integrated Cost-Schedule Risk

PM-042: Joint Cost-Schedule Monte Carlo

The integrated simulation runs cost and schedule Monte Carlo simultaneously, capturing the correlation between duration overruns and cost overruns (longer durations → more time-dependent costs → higher total cost).

| Time-Dependent Cost | Rate | Impact of Schedule Overrun |
| --- | --- | --- |
| General conditions / supervision | $15K–$50K / month | Direct proportional increase |
| Equipment standby | $5K–$20K / month | Direct proportional increase |
| Temporary facilities | $2K–$10K / month | Direct proportional increase |
| Escalation on remaining work | 2–5% annual | Compounds on delayed work |
| Extended overhead | Per contract terms | May be claimable or absorbed |
| Liquidated damages | Per contract terms | Triggered by milestone miss |

# 5. Change Order Management

Change orders are a primary workflow for the automation agent. The system evaluates proposed changes against cost, schedule, and specification impacts using deterministic calculations, routes for appropriate approval, and generates narrative summaries with AI augmentation.

## 5.1 Change Order Model

class ChangeOrder(BaseModel):

co_number: str

project_id: str

title: str

description: str

status: COStatus

initiated_by: str

date_initiated: date

# Classification

change_type: Literal[

'owner_directed',            # Owner requests scope change

'design_change',             # Design revision needed

'differing_site_conditions', # Type I or II DSC

'value_engineering',          # Cost-saving proposal

'regulatory',                # Code/permit requirement change

'force_majeure',             # Unforeseeable event

'constructive_change',       # Informal direction

]

# Impact Analysis

cost_impact: ChangeOrderCostImpact

schedule_impact: ChangeOrderScheduleImpact

spec_impact: ChangeOrderSpecImpact

# Approval

approval_authority: str          # Based on authority matrix

approval_status: Literal['pending','approved','rejected','negotiating']

approval_date: Optional[date]

class COStatus(str, Enum):

DRAFT = 'draft'

PRICING = 'pricing'

SUBMITTED = 'submitted'

IN_REVIEW = 'in_review'

APPROVED = 'approved'

REJECTED = 'rejected'

WITHDRAWN = 'withdrawn'

## 5.2 Cost Impact Analysis

PM-050: Change Order Cost Calculation

CO Cost = Direct Cost + Markup = Σ(Qty × Unit Price) × (1 + OH%) × (1 + Profit%)

class ChangeOrderCostImpact(BaseModel):

# Added work

added_items: List[LineItem]

added_direct_cost: Decimal

# Deleted work (credit)

deleted_items: List[LineItem]

deleted_credit: Decimal

# Net direct

net_direct_cost: Decimal

# Markup (per contract terms)

overhead_pct: Decimal            # Typically 15%

profit_pct: Decimal              # Typically 10%

bond_pct: Decimal                # Typically 1%

markup_on_sub: Decimal           # Typically 5% OH + 5% profit

# Totals

@computed_field

@property

def total_markup(self) -> Decimal:

self_work = self.net_direct_cost * (1 + self.overhead_pct) * (1 + self.profit_pct)

return self_work - self.net_direct_cost

@computed_field

@property

def total_change_cost(self) -> Decimal:

return self.net_direct_cost + self.total_markup

## 5.3 Schedule Impact Analysis

PM-051: Time Impact Analysis (TIA)

The Time Impact Analysis method inserts a “change fragment” into the CPM network and recalculates to determine if the change affects the critical path and project completion date.

class ChangeOrderScheduleImpact(BaseModel):

# Fragment activities

added_activities: List[Activity]

added_relationships: List[Relationship]

modified_activities: List[ActivityModification]

# Impact results (from TIA engine)

original_completion: date

revised_completion: date

net_delay_days: int

critical_path_affected: bool

float_consumed: Dict[str, int]   # activity -> float days consumed

class ActivityModification(BaseModel):

activity_id: str

modification_type: Literal['duration_change', 'logic_change',

'calendar_change', 'constraint_change']

original_value: str

revised_value: str

| TIA Step | Action | Engine Role |
| --- | --- | --- |
| 1. Snapshot baseline | Capture current CPM state | Automated |
| 2. Insert fragment | Add change activities + logic | User defines, engine validates |
| 3. Recalculate CPM | Run forward/backward pass | Automated |
| 4. Compare results | New finish vs. original finish | Automated |
| 5. Identify impacts | Which activities lost float, new CP | Automated |
| 6. Generate narrative | Explain impact in plain language | AI-Augmented |

## 5.4 Approval Authority Matrix

The agent routes change orders to the appropriate approval authority based on cost threshold, schedule impact, and change type.

| Threshold | Approval Authority | Response Time |
| --- | --- | --- |
| Cost < $10K, no schedule impact | Project Manager | 3 business days |
| Cost $10K–$50K, ≤5 day delay | Program Manager | 5 business days |
| Cost $50K–$250K, ≤20 day delay | Director of Construction | 10 business days |
| Cost $250K–$1M | VP of Engineering | 15 business days |
| Cost > $1M or critical path delay >20 days | Executive Committee | 20 business days |
| Differing Site Conditions (any amount) | Program Manager + Legal | 15 business days |
| Value Engineering (any amount) | Project Manager + Designer | 10 business days |

IMPORTANT: The agent enforces the authority matrix. If a PM attempts to approve a $75K change order, the agent intercepts and routes to the Program Manager. The authority matrix is configurable per organization/contract.

## 5.5 Specification Impact Check

Every change order is cross-checked against the specification for compliance:

class ChangeOrderSpecImpact(BaseModel):

affected_spec_sections: List[str]

spec_revisions_needed: List[SpecRevisionImpact]

new_submittals_required: List[SubmittalRequirement]

testing_impact: TestingImpactAssessment

conflicts_detected: List[SpecConflict]

class TestingImpactAssessment(BaseModel):

additional_tests: List[TestingRequirement]

additional_testing_cost: Decimal

testing_schedule_impact: int     # Days for additional testing

# 6. Resource Management

The resource engine tracks labor, equipment, and material resource assignments against availability constraints. Resource leveling adjusts activity timing (within float) to avoid over-allocation without extending the project duration.

## 6.1 Resource Model

class Resource(BaseModel):

resource_id: str

name: str

resource_type: Literal['labor', 'equipment', 'material']

unit: str                        # 'person', 'unit', 'CY'

max_availability: Decimal         # per period (day/week/month)

calendar_id: str

cost_rate: Decimal               # $/unit-period

class ResourceAssignment(BaseModel):

resource_id: str

activity_id: str

units_per_period: Decimal         # e.g., 2.0 operators/day

assignment_type: Literal['fixed_duration', 'fixed_units', 'fixed_work']

class ResourceProfile(BaseModel):

"""Time-phased resource demand for an activity or project."""

resource_id: str

periods: List[ResourcePeriod]

class ResourcePeriod(BaseModel):

period_start: date

period_end: date

demand: Decimal                   # Units needed

available: Decimal                # Units available

over_allocated: bool              # demand > available

## 6.2 Resource Leveling Algorithm

PM-060: Heuristic Resource Leveling

The leveling algorithm delays non-critical activities (within their float) to resolve resource over-allocations. Priority rules determine which activities are delayed first.

| Priority Rule | Description | When Preferred |
| --- | --- | --- |
| Minimum Total Float | Delay activity with most float first | Protect near-critical activities |
| Minimum Late Finish | Delay activity finishing latest first | Protect early milestones |
| Maximum Duration | Delay longest activity first | Minimize number of delays |
| Minimum Resource Demand | Delay least resource-intensive first | Maximize resource utilization |
| Activity Priority | User-assigned priority override | When business logic overrides algorithm |

class ResourceLevelingConfig(BaseModel):

priority_rules: List[str]         # Ordered list of rules to apply

allow_splitting: bool = False     # Can activities be interrupted?

max_project_extension: int = 0    # Days beyond CP allowed (0 = none)

protected_activities: List[str]   # Never delay these

class LevelingResult(BaseModel):

original_finish: date

leveled_finish: date

activities_delayed: List[ActivityDelay]

remaining_overallocations: List[ResourceOverallocation]

resource_utilization: Dict[str, float]  # resource -> avg utilization %

## 6.3 Resource Loading from Cost Estimate

Resource assignments are derived from the Cost Estimating domain’s crew compositions and production rates, creating a direct link between the cost estimate and the schedule resource profile.

| Cost Estimate Field | Schedule Resource | Derivation |
| --- | --- | --- |
| Crew composition (laborers) | Labor resource demand | Count × duration = labor-days |
| Crew composition (equipment) | Equipment resource demand | Count × duration = equip-days |
| Daily output + quantity | Activity duration | Qty / (output × crews) = days |
| Material quantities | Material delivery schedule | Qty phased by activity timing |
| Subcontractor scope | Subcontractor resource | Duration from sub schedule |

# 7. Schedule Delay Analysis

When disputes arise over project delays, forensic schedule analysis determines causation and responsibility. The engine supports multiple accepted delay analysis methods per AACE Recommended Practice 29R-03.

## 7.1 Delay Analysis Methods

| Method | Approach | Complexity | Best For |
| --- | --- | --- | --- |
| As-Planned vs. As-Built | Compare baseline to actual dates | Low | Simple delays, low-value claims |
| Impacted As-Planned | Insert delay into baseline, recalculate | Moderate | Prospective analysis, early claims |
| Collapsed As-Built | Remove delays from as-built, recalculate | Moderate | Retrospective, single-cause delays |
| Time Impact Analysis (TIA) | Insert fragments at each delay event | High | Complex delays, government contracts |
| Windows Analysis | Divide project into periods, analyze each | High | Multiple concurrent delays |
| As-Planned But-For | Show what would have happened without delay | Moderate | Clear single-party delays |

## 7.2 Delay Classification

| Delay Type | Responsibility | Time Extension? | Compensation? |
| --- | --- | --- | --- |
| Excusable, Compensable | Owner-caused | Yes | Yes (time + money) |
| Excusable, Non-Compensable | Neither party (force majeure, weather) | Yes | No (time only) |
| Non-Excusable | Contractor-caused | No | No |
| Concurrent | Both parties simultaneously | Often yes | Often no (depends on jurisdiction) |

## 7.3 Weather Delay Equations

PM-070: Excusable Weather Days

Excusable Weather Days = Actual Lost Days - Anticipated Lost Days (per contract)

| Month | Denver Avg Lost Days | Houston Avg | Seattle Avg | Chicago Avg |
| --- | --- | --- | --- | --- |
| January | 6–8 | 4–6 | 10–13 | 8–11 |
| February | 5–7 | 4–5 | 8–11 | 7–10 |
| March | 5–7 | 4–6 | 8–10 | 6–9 |
| April | 4–6 | 4–6 | 6–9 | 5–8 |
| May | 4–6 | 5–7 | 4–7 | 4–7 |
| June | 2–4 | 5–8 | 3–5 | 3–5 |
| July | 2–4 | 4–6 | 1–3 | 2–4 |
| August | 2–4 | 4–6 | 1–3 | 2–4 |
| September | 2–4 | 5–8 | 2–5 | 3–5 |
| October | 3–5 | 4–6 | 5–8 | 4–7 |
| November | 4–6 | 3–5 | 8–11 | 6–9 |
| December | 5–8 | 4–6 | 10–13 | 8–11 |
| Annual Total | 44–69 | 50–75 | 66–97 | 58–84 |

Basis: NOAA historical precipitation and temperature data. ‘Lost day’ = day with >0.25” precipitation or temperature <20°F for outdoor earthwork operations. Criteria vary by work type—concrete placement is more weather-sensitive than earthwork.

# 8. Equation Catalog & Reference Data

## 8.1 Complete PM Equation Catalog

| ID | Name | Formula | Type |
| --- | --- | --- | --- |
| PM-001 | Early Start | ES = max(EF_pred + lag) | CPM |
| PM-002 | Early Finish | EF = ES + Duration - 1 | CPM |
| PM-003 | Late Finish | LF = min(LS_succ - lag) | CPM |
| PM-004 | Late Start | LS = LF - Duration + 1 | CPM |
| PM-005 | Total Float | TF = LS - ES | CPM |
| PM-006 | Free Float | FF = min(ES_succ) - EF | CPM |
| PM-007 | Critical Path | {activities where TF = 0} | CPM |
| PM-008 | Production Duration | Qty / (Output × Crews × Eff) | Duration |
| PM-009 | PERT Duration | (O + 4M + P) / 6 | Duration |
| PM-010 | Learning Curve | T_n = T_1 × n^(log(LR)/log(2)) | Duration |
| PM-020 | BAC | Total baseline budget | EVM |
| PM-021 | PV (BCWS) | Planned% × BAC | EVM |
| PM-022 | EV (BCWP) | Actual% × BAC | EVM |
| PM-023 | AC (ACWP) | Σ actual costs | EVM |
| PM-024 | SV | EV - PV | EVM |
| PM-025 | CV | EV - AC | EVM |
| PM-026 | SPI | EV / PV | EVM |
| PM-027 | CPI | EV / AC | EVM |
| PM-028 | SV% | SV / PV × 100 | EVM |
| PM-029 | CV% | CV / EV × 100 | EVM |
| PM-030 | EAC (CPI) | BAC / CPI | EVM Forecast |
| PM-031 | EAC (Composite) | AC + (BAC-EV)/(CPI×SPI) | EVM Forecast |
| PM-032 | EAC (New Estimate) | AC + ETC (bottom-up) | EVM Forecast |
| PM-033 | EAC (Budget) | AC + (BAC - EV) | EVM Forecast |
| PM-034 | ETC | EAC - AC | EVM Forecast |
| PM-035 | VAC | BAC - EAC | EVM Forecast |
| PM-036 | TCPI (BAC) | (BAC - EV) / (BAC - AC) | EVM Forecast |
| PM-037 | TCPI (EAC) | (BAC - EV) / (EAC - AC) | EVM Forecast |
| PM-040 | Risk Score | P × max(Cost I, Sched I) | Risk |
| PM-041 | Monte Carlo (Schedule) | N-iter CPM with distributions | Risk |
| PM-042 | Joint Cost-Schedule MC | Integrated cost + schedule sim | Risk |
| PM-050 | Change Order Cost | Σ(Qty×UP) × (1+OH%)(1+Profit%) | Change |
| PM-051 | Time Impact Analysis | Fragment insertion + CPM recalc | Change |
| PM-060 | Resource Leveling | Heuristic delay within float | Resource |
| PM-070 | Excusable Weather | Actual Lost - Anticipated Lost | Delay |

## 8.2 Equation Count Summary

| Category | Count | Type |
| --- | --- | --- |
| CPM Scheduling | 7 | Deterministic |
| Duration Estimation | 3 | Det. + Probabilistic |
| Earned Value Management | 18 | Deterministic |
| Risk Analysis | 3 | Probabilistic |
| Change Order Processing | 2 | Deterministic |
| Resource Management | 1 | Algorithmic |
| Delay Analysis | 1 | Deterministic |
| TOTAL | 35 |  |

## 8.3 Reference Data Tables

| Data Table | Records | Source | Update |
| --- | --- | --- | --- |
| Weather Lost Day Averages | ~50 cities × 12 months | NOAA historical | Decadal |
| Learning Curve Rates | ~20 activity types | Published references | Static |
| EVM Alert Thresholds | ~10 conditions | Agency/org standards | Configurable |
| Approval Authority Matrix | ~7 threshold levels | Organization policy | Configurable |
| Change Order Markup Rates | ~10 contract types | FAR/contract terms | Per contract |
| Percent Complete Methods | ~7 methods | AACE/PMI practice | Static |
| Delay Analysis Methods | ~6 methods | AACE RP 29R-03 | Static |
| Resource Leveling Priority Rules | ~5 rules | PMI/scheduling practice | Static |
| Calendar Templates | ~5 standard calendars | Industry practice | Configurable |
| Report Templates (CPR) | ~7 formats | DI-MGMT-81466A | Per contract |