ENGR-KB

Engineering Knowledge Base

Construction Engineering

Equipment, Production Rates, Methods, Deep Foundations & GeoLab Integration

v1.0  |  February 2026

ENGR-KB Document Series  |  Document 5 of 6

DRAFT — INTERNAL USE ONLY

# Table of Contents

# 1. Construction Engineering Domain Overview

The Construction Engineering domain provides the physical execution layer of the knowledge base—how work actually gets built. It covers equipment selection, production rate calculation, construction method planning, temporary works, and site condition adjustments. This domain is the bridge between what a project costs (Cost Estimating) and how long it takes (Project Management), with soil/rock properties from GeoLab driving nearly every calculation.

Core Design Principle: Production rates and equipment capabilities are deterministic calculations based on manufacturer specifications, published performance data, and empirically-derived correction factors. AI augmentation is limited to method recommendation (suggesting which approach to use) and interpreting non-standard site conditions. The physics of how a roller compacts soil or how a truck hauls material does not benefit from AI inference.

## 1.1 Scope of Coverage

| Category | Sub-Categories | Equations | Primary Data Sources |
| --- | --- | --- | --- |
| Equipment Library | Specs, rates, selection | ~15 | Manufacturer data, USACE EP 1110-1-8 |
| Earthwork Production | Excavation, haul, compact, grade | ~25 | Caterpillar PHB, USACE, field data |
| Deep Foundations | Driven piles, drilled shafts, micropiles | ~12 | FHWA manuals, published case data |
| Ground Improvement | Compaction grouting, stone columns, wick drains | ~10 | FHWA, specialty contractor data |
| Dewatering | Wellpoints, deep wells, cutoff walls | ~8 | Groundwater engineering references |
| Concrete Placement | Pump, crane, tremie, batch plant | ~8 | ACI, equipment manufacturer data |
| Tunneling | TBM, NATM/SEM, cut-and-cover | ~6 | Published tunnel performance data |
| Temporary Works | Shoring, cofferdam, access roads | ~6 | Design references, field practice |

## 1.2 Domain Integration Points

| From Domain | Data Flow | To Domain | Purpose |
| --- | --- | --- | --- |
| GeoLab | Soil classification, density, strength, permeability | Const. Eng. | Equipment selection, production factors |
| Const. Eng. | Production rates, durations | Project Mgmt | Activity duration calculation |
| Const. Eng. | Equipment rates, crew costs | Cost Estimating | Unit cost development |
| Specifications | Method constraints, QC requirements | Const. Eng. | Method selection constraints |
| Const. Eng. | Method capabilities, limitations | Specifications | Achievable tolerance/quality input |

# 2. Equipment Library & Rate Calculation

The equipment library maintains specifications, ownership costs, and operating costs for construction equipment commonly used in geotechnical and heavy civil construction. Hourly rates follow the USACE EP 1110-1-8 methodology.

## 2.1 Equipment Specification Model

class Equipment(BaseModel):

equipment_id: str

category: EquipmentCategory

make: str

model: str

description: str

# Performance Specs

horsepower: Decimal

operating_weight: Decimal        # lbs

bucket_capacity: Optional[Decimal]  # CY (heaped)

blade_width: Optional[Decimal]   # ft

drum_width: Optional[Decimal]    # ft (rollers)

max_depth: Optional[Decimal]     # ft (excavators)

max_reach: Optional[Decimal]     # ft

payload_capacity: Optional[Decimal]  # tons or CY

# Economic Life

purchase_price: Decimal

salvage_value: Decimal

useful_life_hours: int           # Total economic life in hours

useful_life_years: int

annual_operating_hours: int = 2000

# Operating Parameters

fuel_consumption_gph: Decimal    # Gallons per hour at full load

fuel_type: Literal['diesel', 'gasoline', 'electric']

load_factor: Decimal             # Typical % of rated HP used

tire_life_hours: Optional[int]   # For rubber-tired equipment

tire_cost: Optional[Decimal]     # Full set replacement

class EquipmentCategory(str, Enum):

EXCAVATOR = 'excavator'

DOZER = 'dozer'

LOADER = 'loader'

SCRAPER = 'scraper'

GRADER = 'grader'

ROLLER = 'roller'

HAUL_TRUCK = 'haul_truck'

CRANE = 'crane'

DRILL_RIG = 'drill_rig'

PILE_DRIVER = 'pile_driver'

CONCRETE_PUMP = 'concrete_pump'

BATCH_PLANT = 'batch_plant'

GENERATOR = 'generator'

PUMP = 'pump'

COMPRESSOR = 'compressor'

## 2.2 Equipment Hourly Rate Equations

CN-EQP-001: Total Equipment Hourly Rate

Hourly Rate = Ownership Rate + Operating Rate

### 2.2.1 Ownership Cost Components

CN-EQP-002: Depreciation

Depreciation/hr = (Purchase Price - Salvage Value) / Useful Life Hours

CN-EQP-003: Cost of Money (Interest)

Interest/hr = ((Purchase + Salvage) / 2) × Annual Rate / Annual Hours

CN-EQP-004: Insurance

Insurance/hr = Average Value × Insurance Rate / Annual Hours

CN-EQP-005: Property Tax

Tax/hr = Assessed Value × Tax Rate / Annual Hours

### 2.2.2 Operating Cost Components

CN-EQP-006: Fuel Cost

Fuel/hr = HP × Load Factor × SFC (gal/HP-hr) × Fuel Price ($/gal)

| Fuel Parameter | Diesel | Gasoline | Notes |
| --- | --- | --- | --- |
| Specific Fuel Consumption (SFC) | 0.04 gal/HP-hr | 0.06 gal/HP-hr | At rated load |
| Typical Load Factor (earthwork) | 0.50–0.65 | 0.40–0.55 | Varies by application |
| Typical Load Factor (lifting) | 0.40–0.50 | — | Crane, pile driver |
| Fuel price (reference) | $3.50–$4.50/gal | $3.00–$4.00/gal | 2024 avg, varies regionally |

CN-EQP-007: Lubrication

Lube/hr = Fuel Cost/hr × 0.10 to 0.15 (10-15% of fuel cost)

CN-EQP-008: Tire Cost (rubber-tired equipment)

Tires/hr = Tire Set Replacement Cost / Tire Life Hours

CN-EQP-009: Repair Reserve

Repair/hr = Depreciation/hr × Repair Factor (0.50 to 0.80)

## 2.3 Representative Equipment Rate Table

The following represents reference hourly rates calculated using the USACE methodology. Rates are for 2024, Denver area basis, with 2,000 annual operating hours.

| Equipment | HP | Own ($/hr) | Oper ($/hr) | Total ($/hr) | Operator ($/hr) |
| --- | --- | --- | --- | --- | --- |
| Excavator, 1.0 CY (20-ton) | 148 | $28 | $22 | $50 | $62 |
| Excavator, 2.0 CY (36-ton) | 268 | $45 | $34 | $79 | $62 |
| Excavator, 3.5 CY (60-ton) | 400 | $72 | $48 | $120 | $65 |
| Dozer, D6 class (165 HP) | 165 | $35 | $25 | $60 | $62 |
| Dozer, D8 class (310 HP) | 310 | $58 | $40 | $98 | $65 |
| Dozer, D9 class (410 HP) | 410 | $75 | $52 | $127 | $65 |
| Wheel Loader, 3.0 CY | 175 | $32 | $28 | $60 | $62 |
| Wheel Loader, 5.0 CY | 310 | $52 | $40 | $92 | $62 |
| Motor Grader, 14-ft blade | 225 | $40 | $30 | $70 | $62 |
| Vibratory Roller, 10-ton | 130 | $22 | $18 | $40 | $55 |
| Sheepsfoot Roller, 20-ton | 200 | $30 | $24 | $54 | $55 |
| Off-highway Truck, 25-ton | 350 | $42 | $48 | $90 | $58 |
| Off-highway Truck, 40-ton | 500 | $60 | $62 | $122 | $58 |
| Articulated Truck, 30-ton | 375 | $48 | $52 | $100 | $58 |
| Scraper, 21 CY (self-load) | 450 | $65 | $55 | $120 | $62 |
| Crane, 80-ton crawler | 260 | $65 | $35 | $100 | $68 |
| Crane, 200-ton crawler | 350 | $120 | $50 | $170 | $72 |
| Concrete Pump, 36m boom | 300 | $55 | $35 | $90 | $65 |
| Drill Rig (foundation) | 250 | $70 | $40 | $110 | $68 |
| Pile Driver (diesel hammer) | N/A | $45 | $30 | $75 | $65 |

IMPORTANT: These are reference rates calculated using the USACE methodology with standard assumptions (2,000 hr/yr, 6% cost of money, standard insurance/tax). Actual rates vary significantly by fleet age, utilization, maintenance practices, and local market. Users should calibrate with their own fleet data or current rental rates.

## 2.4 Altitude Derating

CN-EQP-010: Engine Derating for Altitude

Derated HP = Rated HP × (1 - 0.03 × ((Altitude - 2500) / 1000))  for alt > 2,500 ft

| Altitude (ft) | Derating | Effective HP (300 HP rated) | Impact |
| --- | --- | --- | --- |
| 0–2,500 | 0% | 300 HP | No derating needed |
| 3,500 | 3% | 291 HP | Minimal—most work unaffected |
| 5,000 | 7.5% | 278 HP | Noticeable on heavy earthwork |
| 6,000 | 10.5% | 269 HP | Plan for reduced production |
| 7,500 | 15% | 255 HP | Significant production reduction |
| 10,000 | 22.5% | 233 HP | Major impact, consider larger equipment |

IMPORTANT: Denver sits at ~5,280 ft elevation. All Colorado Front Range projects should apply approximately 8% derating. Mountain projects (ski areas, mine sites, reservoirs) at 8,000-10,000 ft face 15-22% production loss. The system automatically applies altitude derating when project elevation is specified.

# 3. Earthwork Production Rate Engine

GEOLAB BRIDGE

Production rates are the quantitative link between equipment capability and soil behavior. Every rate in this section is parameterized by soil properties from GeoLab testing.

## 3.1 Excavation Production

CN-EXC-001: Excavator Production Rate

Production (BCY/hr) = Bucket Cap (LCY) × Fill Factor × Cycles/hr × Efficiency

| Variable | Description | Source |
| --- | --- | --- |
| Bucket Capacity | Heaped bucket volume (LCY) | Equipment specs (SAE rated) |
| Fill Factor | % of bucket actually filled per cycle | Soil type (GeoLab classification) |
| Cycles/hr | 60 / cycle time (minutes) | Swing angle, depth, truck positioning |
| Efficiency | Operating efficiency factor | Job conditions, management |

### 3.1.1 Fill Factors by Soil Type (GeoLab-Derived)

| USCS Class | Description | Fill Factor | Cycle Adjust | Notes |
| --- | --- | --- | --- | --- |
| GW, GP | Gravel (clean) | 0.85–0.95 | 1.00 | Free-flowing, easy loading |
| SW, SP | Sand (clean) | 0.85–0.95 | 1.00 | Free-flowing, may run from bucket |
| GM, SM | Silty gravel/sand | 0.80–0.90 | 1.00–1.05 | Good loading, slight adhesion |
| GC, SC | Clayey gravel/sand | 0.75–0.85 | 1.05–1.10 | Some adhesion, clumping |
| ML | Low-plasticity silt | 0.70–0.80 | 1.05–1.10 | Sticks to bucket when wet |
| CL | Low-plasticity clay | 0.65–0.80 | 1.10–1.15 | Adhesion, harder to fill/dump |
| MH | High-plasticity silt | 0.60–0.75 | 1.10–1.20 | Significant adhesion |
| CH | High-plasticity clay | 0.55–0.70 | 1.15–1.25 | Heavy adhesion, slow dump |
| OL, OH | Organic soils | 0.50–0.70 | 1.10–1.25 | Variable, may be fibrous |
| Rock (blasted) | Shot rock, rip-rap | 0.60–0.75 | 1.10–1.20 | Irregular shapes, voids |
| Rock (ripped) | Ripped material | 0.65–0.80 | 1.05–1.15 | Mixed sizes |

### 3.1.2 Excavator Cycle Time

CN-EXC-002: Excavator Cycle Time

Cycle (sec) = Dig + Swing Loaded + Dump + Swing Empty

| Component | Typical Range | Factors |
| --- | --- | --- |
| Dig time | 5–12 sec | Soil hardness, depth, bucket size |
| Swing loaded (90°) | 4–6 sec | Machine size, operator skill |
| Swing loaded (180°) | 6–9 sec | Long swing = lower production |
| Dump time | 2–5 sec | Soil adhesion, truck height |
| Swing empty (return) | 3–5 sec | Slightly faster than loaded |
| Typical total cycle | 15–30 sec | 2–4 cycles per minute |

## 3.2 Dozer Production

CN-DOZ-001: Dozer Production Rate (Slot Dozing)

Production (LCY/hr) = Blade Cap (LCY) × (60 / Cycle min) × Efficiency × Grade Factor

CN-DOZ-002: Dozer Cycle Time

Cycle (min) = (Push Dist / Push Speed) + (Return Dist / Return Speed) + Fixed Time

| Push Distance (ft) | D6 Class (LCY/hr) | D8 Class (LCY/hr) | D9 Class (LCY/hr) |
| --- | --- | --- | --- |
| 50 | 350–500 | 550–750 | 700–950 |
| 100 | 250–380 | 400–575 | 500–725 |
| 150 | 180–280 | 300–440 | 380–560 |
| 200 | 140–220 | 230–350 | 300–450 |
| 300 | 90–150 | 160–250 | 200–320 |
| 500 | 50–90 | 90–150 | 120–200 |

Note: Values shown for slot dozing in common earth (GW-CL range). Reduce 15–25% for side-by-side dozing. Reduce 20–40% for CH/MH clays (sticky, heavy). Increase 10–20% for downhill push. Caterpillar Performance Handbook is the primary reference.

## 3.3 Hauling Production

CN-HAUL-001: Truck Fleet Production

Fleet Production (LCY/hr) = Truck Cap (LCY) × (60 / Cycle min) × N_trucks × Efficiency

CN-HAUL-002: Fleet Balance (Loader-Truck Matching)

N_trucks = ceil(Truck Cycle Time / Loader Cycle Time per Truck)

Loader Cycle per Truck = (Truck Cap / Loader Bucket Cap) × Loader Cycle Time

| Haul Distance | 25-ton Truck (LCY/hr) | 40-ton Truck (LCY/hr) | Optimal Equipment |
| --- | --- | --- | --- |
| 500 ft (on-site) | 80–120 | 120–180 | Dozer or scraper may be cheaper |
| 0.5 mile | 50–80 | 80–120 | Trucks become cost-effective |
| 1 mile | 35–55 | 55–85 | Trucks preferred |
| 2 miles | 22–38 | 35–58 | Trucks, consider artic. for off-road |
| 5 miles | 12–20 | 18–30 | Highway trucks if paved route |
| 10+ miles | 6–12 | 10–18 | Transfer operation may help |

## 3.4 Compaction Production

CN-CMP-001: Roller Compaction Production Rate

Production (CCY/hr) = (Width_eff × Speed × Lift × Eff) / (Passes × 27)

Where Width_eff = Drum Width - Overlap (typically 6–12 inches per pass)

Speed in ft/hr = mph × 5,280

Lift in ft = compacted lift thickness

27 = cubic feet per cubic yard

### 3.4.1 Soil-Compactor Selection Matrix (GeoLab-Driven)

| USCS | Primary Compactor | Alt. Compactor | Lift (in) | Passes | Speed (mph) | Prod. (CCY/hr) |
| --- | --- | --- | --- | --- | --- | --- |
| GW, GP | Vib. smooth drum | Vib. padfoot | 10–12 | 3–4 | 4–5 | 400–650 |
| SW, SP | Vib. smooth drum | Plate compactor | 10–12 | 3–4 | 4–5 | 400–650 |
| GM, SM | Vib. smooth drum | Vib. sheepsfoot | 6–8 | 4–6 | 3–4 | 250–450 |
| GC, SC | Sheepsfoot | Padfoot | 6–8 | 5–8 | 2–4 | 180–350 |
| ML | Sheepsfoot | Padfoot | 4–6 | 6–8 | 2–3 | 120–250 |
| CL | Sheepsfoot | Padfoot | 4–6 | 6–10 | 2–3 | 100–220 |
| CH | Sheepsfoot | Padfoot | 4–6 | 8–12 | 2–3 | 70–160 |
| MH | Sheepsfoot | Padfoot | 4–6 | 8–12 | 2–3 | 70–160 |

IMPORTANT: Production rates shown assume 0.83 efficiency, 84-inch drum width, and moderate fill area allowing straight passes of 200+ ft. Reduce 30-50% for confined areas (around structures, in trenches). GeoLab Proctor results set the target density; field density testing per spec frequency verifies achievement.

## 3.5 Grading Production

CN-GRD-001: Motor Grader Production Rate

Production (SY/hr) = (Blade Width_eff × Speed × 5280) / (Passes × 9)

| Grading Type | Passes | Speed (mph) | Production (SY/hr) | Tolerance |
| --- | --- | --- | --- | --- |
| Rough grading (fill surfaces) | 2–4 | 3–5 | 3,000–6,000 | ±0.1 ft |
| Intermediate grading | 3–5 | 2–4 | 2,000–4,000 | ±0.05 ft |
| Fine grading (subgrade) | 4–6 | 1.5–3 | 1,000–2,500 | ±0.04 ft |
| Finish grading (paving subgrade) | 4–8 | 1–2 | 600–1,500 | ±0.02 ft |
| Ditch cutting | 2–4 | 2–3 | 1,500–3,000 LF/hr | Per template |
| Road maintenance | 2–3 | 3–5 | 4,000–8,000 SY/hr | N/A |

## 3.6 Scraper Production

CN-SCR-001: Scraper Production Rate

Production (BCY/hr) = Capacity (LCY) × Fill Factor × Load Factor × (60/Cycle) × Eff

| Scraper Type | Capacity (LCY) | Optimal Haul | BCY/hr (1-way mile) | Best Soil Types |
| --- | --- | --- | --- | --- |
| Single engine, 15 CY | 15 | 500–3,000 ft | 150–250 | Sand, sandy gravel |
| Single engine, 21 CY | 21 | 1,000–5,000 ft | 200–350 | Sand, silt, light clay |
| Twin engine, 24 CY | 24 | 1,000–7,000 ft | 250–400 | Most soils except rock/heavy clay |
| Push-loaded, 33 CY | 33 | 2,000–10,000 ft | 300–500 | All soils (with push dozer) |
| Elevating, 14 CY | 14 | 500–3,000 ft | 130–230 | Self-loading, granular preferred |

# 4. Deep Foundation Production

Deep foundation production rates depend heavily on subsurface conditions from GeoLab testing. Soil strength, rock quality, and groundwater conditions directly determine achievable installation rates and therefore both cost and schedule.

## 4.1 Driven Pile Production

CN-PILE-001: Pile Driving Production Rate

Piles/Day = Working Hours / (Move + Setup + Drive + Splice + Cutoff per pile)

| Pile Type | Size Range | Easy Driving | Moderate | Hard Driving | GeoLab Driver |
| --- | --- | --- | --- | --- | --- |
| Steel H-pile | HP 10–14 | 12–18/day | 8–14/day | 4–8/day | SPT-N, soil profile |
| Steel pipe pile | 12–24" dia | 10–16/day | 6–12/day | 3–7/day | SPT-N, rock depth |
| Precast concrete | 12–18" sq | 10–15/day | 6–10/day | 3–6/day | SPT-N, soft layers |
| Timber | 10–12" tip | 15–20/day | 10–15/day | 6–10/day | SPT-N, refusal depth |
| Sheet pile (steel) | PZ-27 to PZ-40 | 500–800 SF/day | 300–600 SF/day | 150–350 SF/day | SPT-N, cobbles/boulders |

| Driving Difficulty | GeoLab Criteria | Blow Count Expectation |
| --- | --- | --- |
| Easy | Predominantly soft to medium soils (N < 20), no obstructions | <40 blows/ft through most of profile |
| Moderate | Medium to dense soils (N = 20-40), minor obstructions | 40–80 blows/ft in bearing layer |
| Hard | Dense soils/soft rock (N > 40), cobbles/boulders, refusal | >80 blows/ft, pre-drilling may be needed |

## 4.2 Drilled Shaft Production

CN-SHAFT-001: Drilled Shaft Production Rate

Shafts/Day = Working Hours / (Setup + Drill + Clean + Cage + Pour + Move)

| Diameter | Depth Range | Soil (ft/hr) | Soft Rock (ft/hr) | Hard Rock (ft/hr) | Casing? |
| --- | --- | --- | --- | --- | --- |
| 24–36" | 20–40 ft | 15–30 | 5–15 | 2–8 | If caving soil |
| 36–48" | 30–60 ft | 12–25 | 4–12 | 1.5–6 | Common |
| 48–72" | 40–80 ft | 8–20 | 3–10 | 1–5 | Common |
| 72–96" | 50–100 ft | 5–15 | 2–8 | 0.5–4 | Usually required |
| 96–120" | 60–120 ft | 3–10 | 1.5–6 | 0.3–3 | Required |

IMPORTANT: GeoLab UCS and RQD data directly determine drilling rates in rock. UCS < 3,000 psi = 'soft rock' rates; 3,000-10,000 psi = 'medium'; >10,000 psi = 'hard rock' rates. Caving soils (loose sand below water table, soft clay) require casing or slurry, adding 20-40% to cycle time. GeoLab permeability and classification data identify caving risk.

## 4.3 Micropile Production

CN-MICRO-001: Micropile Installation Rate

Micropiles/Day = Working Hours / (Drill + Flush + Cage + Grout + Move)

| Diameter | Ground Conditions | Drilling Rate (ft/hr) | Piles/Day (40 ft avg) |
| --- | --- | --- | --- |
| 6–8" | Soil, no obstructions | 20–40 | 3–6 |
| 6–8" | Soil with cobbles/boulders | 10–25 | 2–4 |
| 6–8" | Soft to medium rock | 8–18 | 1.5–3 |
| 6–8" | Hard rock (>10,000 psi) | 3–10 | 0.5–2 |
| 8–12" | Any (add 20–40% to cycle) | Varies | 60–75% of 6-8" rates |

# 5. Dewatering & Ground Improvement

## 5.1 Dewatering Production & Sizing

CN-DW-001: Wellpoint System Flow Rate (Darcy’s Law)

Q = k × i × A  (total flow to dewatering system)

Where k = hydraulic conductivity (GeoLab permeability test), i = hydraulic gradient, A = area perpendicular to flow.

CN-DW-002: Number of Wellpoints Required

N = Perimeter (ft) / Spacing (ft)  [typically 3–6 ft spacing]

| Dewatering Method | Applicable k Range | Max Drawdown | GeoLab Data | Relative Cost |
| --- | --- | --- | --- | --- |
| Wellpoints (single stage) | 10⁻² to 10⁻⁴ cm/s | 15–18 ft | Permeability, gradation | Low–Moderate |
| Wellpoints (multi-stage) | 10⁻² to 10⁻⁴ cm/s | 30–40 ft | Permeability, stratigraphy | Moderate |
| Deep wells | 10⁻¹ to 10⁻³ cm/s | 50–100+ ft | Transmissivity, storativity | Moderate–High |
| Eductor wells | 10⁻³ to 10⁻⁵ cm/s | 50–80 ft | Permeability (low-k soils) | High |
| Sump pumping | > 10⁻² cm/s | 5–10 ft | Permeability, gradation | Very Low |
| Cutoff wall (soil-bentonite) | Any (barrier) | N/A (barrier) | Permeability of barrier | High |
| Sheet pile cutoff | Moderate seepage | N/A (barrier) | Driving conditions | Moderate–High |

WARNING: GeoLab permeability testing is the single most important input for dewatering design. A factor of 10 error in k (common with empirical estimates) can mean the difference between a $50K wellpoint system and a $500K deep well system. Always use lab-measured k from GeoLab when available.

## 5.2 Ground Improvement Methods

| Method | Applicable Soils | Improvement | Production Rate | GeoLab Data |
| --- | --- | --- | --- | --- |
| Vibro-compaction | Clean sand (< 15% fines) | Densify to 70-85% Dr | 3–8 points/day | Gradation, Dr, SPT-N |
| Stone columns | Soft clay, silt, loose sand | Increase bearing, reduce settle. | 2–5 columns/day | Shear strength, settlement |
| Wick drains | Soft clay, organic deposits | Accelerate consolidation | 100–300 LF/day | Cv, permeability, Cc |
| Compaction grouting | Loose sand, silt, fill | Densify by displacement | 5–15 CY grout/day | SPT-N, void ratio |
| Jet grouting | Any soil | Create soilcrete columns | 1–3 columns/day | Gradation, strength, k |
| Deep soil mixing | Soft clay, organic, peat | Cement-soil columns | 3–8 columns/day | Moisture, organic, strength |
| Dynamic compaction | Granular, fill, rubble | Densify by impact | 500–2,000 SF/day | Gradation, groundwater depth |
| Rapid impact compaction | Granular fill | Densify shallow soils | 2,000–5,000 SF/day | Gradation, SPT-N |

## 5.3 Ground Improvement Equations

CN-GI-001: Wick Drain Time for Consolidation

t = (D_e² / (8 × C_h)) × ln(1 / (1 - U%))  × F(n) × F(s)

Where D_e = effective drain diameter, C_h = horizontal coefficient of consolidation (GeoLab), U% = target degree of consolidation, F(n) = drain spacing function, F(s) = smear zone function.

CN-GI-002: Stone Column Area Replacement Ratio

a_s = A_col / A_total = (π d² / 4) / (s² × C_pattern)

Where d = column diameter, s = spacing, C_pattern = pattern constant (0.866 for triangular, 1.0 for square).

CN-GI-003: Grouting Volume Estimate

Grout Volume = Void Volume × (1 + Waste Factor) / Grout Take Factor

Void Volume = Treatment Volume × Porosity (from GeoLab)

# 6. Concrete Placement & Specialty Operations

## 6.1 Concrete Placement Rates

CN-CONC-001: Concrete Pump Output

Output (CY/hr) = Pipe Area × Piston Strokes/min × 60 × Efficiency / 27

| Placement Method | Rate (CY/hr) | Max Distance/Height | Best Application |
| --- | --- | --- | --- |
| Direct chute (truck) | 15–25 | 10–15 ft reach | Slabs, footings at grade |
| Conveyor | 40–80 | 200 ft horizontal | High-volume continuous |
| Crane & bucket (1 CY) | 10–20 | Per crane capacity | Structural, elevated |
| Crane & bucket (3 CY) | 20–40 | Per crane capacity | Mass concrete, walls |
| Boom pump (36m) | 40–80 | 120 ft reach | Most common—versatile |
| Boom pump (52m) | 60–100 | 170 ft reach | High-rise, large pours |
| Line pump | 25–50 | 500+ ft horizontal | Slabs, long horizontal runs |
| Tremie (underwater) | 5–15 | Below water | Drilled shafts, cofferdam seals |

## 6.2 Concrete Production Factors

| Factor | Impact | Source |
| --- | --- | --- |
| Congested rebar | Reduce pump rate 20–40% | Rebar density from structural design |
| Hot weather (>90°F) | Reduce window, add retarder cost | Site climate data |
| Cold weather (<40°F) | Heating, blankets, longer cure | Site climate data |
| Mass concrete (>4 ft thick) | Temperature control, reduced pour rate | Thermal analysis |
| High-strength (>6000 psi) | Longer cure, more QC testing | Mix design from spec |
| Self-consolidating (SCC) | Faster placement, no vibrating, +15–30% mat cost | Mix design from spec |
| Architectural finish | Slower placement, form prep, +cost | Spec finish requirements |
| Fiber reinforced | Possible pump issues, slower | Mix design from spec |

## 6.3 Tunneling Production (Reference)

CN-TUN-001: TBM Advance Rate

Advance (ft/day) = RPM × Penetration/rev × 60 × Operating Hours × Utilization

| Ground Condition | Penetration (in/rev) | Utilization | Advance (ft/day) | GeoLab Data |
| --- | --- | --- | --- | --- |
| Soft ground (clay, silt) | 0.5–2.0 | 40–60% | 30–70 | Shear strength, permeability |
| Mixed face | 0.3–1.0 | 25–45% | 15–40 | Soil/rock interface, UCS |
| Soft rock (UCS <5,000 psi) | 0.15–0.5 | 35–55% | 20–50 | UCS, abrasivity (CAI) |
| Medium rock (5K–15K psi) | 0.05–0.20 | 30–50% | 10–35 | UCS, RQD, joint spacing |
| Hard rock (>15,000 psi) | 0.02–0.10 | 25–45% | 5–20 | UCS, abrasivity, quartz content |

## 6.4 Site Condition Adjustment Factors

All production rates in this domain are adjusted for site conditions using multiplicative factors. These factors apply to any activity performed on site.

| Factor | Favorable | Average | Unfavorable | Severe |
| --- | --- | --- | --- | --- |
| Job efficiency (management) | 0.90 | 0.83 | 0.75 | 0.65 |
| Operator skill | 1.00 | 0.90–0.95 | 0.80–0.85 | 0.70–0.75 |
| Equipment condition | 1.00 | 0.90–0.95 | 0.80–0.90 | 0.70–0.80 |
| Site congestion | 1.00 | 0.90–0.95 | 0.75–0.85 | 0.60–0.70 |
| Material availability | 1.00 | 0.95 | 0.85–0.90 | 0.70–0.80 |
| Temperature (<20°F or >100°F) | N/A | 1.00 | 0.80–0.90 | 0.50–0.70 |
| Altitude (per CN-EQP-010) | 1.00 (<2,500 ft) | 0.92 (5,000 ft) | 0.85 (7,500 ft) | 0.78 (10,000 ft) |
| Visibility/night work | 1.00 (daylight) | 0.95 | 0.85–0.90 | 0.75–0.80 |

Combining Factors: Multiply all applicable factors. A high-altitude (0.85), congested (0.80), night-shift (0.85) operation: 0.85 × 0.80 × 0.85 = 0.578—roughly 58% of standard production. This compound effect is why mountain construction projects routinely exceed lowland cost estimates.

# 7. Equation Catalog & Reference Data

## 7.1 Complete Construction Engineering Equation Catalog

| ID | Name | Formula Summary | Category |
| --- | --- | --- | --- |
| CN-EQP-001 | Equipment Hourly Rate | Ownership/hr + Operating/hr | Equipment |
| CN-EQP-002 | Depreciation | (Purchase - Salvage) / Life Hours | Equipment |
| CN-EQP-003 | Cost of Money | ((P+S)/2) × Rate / Annual Hr | Equipment |
| CN-EQP-004 | Insurance | Avg Value × Rate / Annual Hr | Equipment |
| CN-EQP-005 | Property Tax | Assessed × Rate / Annual Hr | Equipment |
| CN-EQP-006 | Fuel Cost | HP × LF × SFC × $/gal | Equipment |
| CN-EQP-007 | Lubrication | Fuel Cost × 0.10–0.15 | Equipment |
| CN-EQP-008 | Tire Cost | Set Cost / Tire Life Hours | Equipment |
| CN-EQP-009 | Repair Reserve | Depreciation × 0.50–0.80 | Equipment |
| CN-EQP-010 | Altitude Derating | HP × (1-0.03×((alt-2500)/1000)) | Equipment |
| CN-EXC-001 | Excavator Production | Cap × FF × Cycles × Eff | Earthwork |
| CN-EXC-002 | Excavator Cycle Time | Dig+Swing+Dump+Return | Earthwork |
| CN-DOZ-001 | Dozer Production | Blade × (60/Cycle) × Eff × Grade | Earthwork |
| CN-DOZ-002 | Dozer Cycle Time | Push/Speed + Return/Speed + Fixed | Earthwork |
| CN-HAUL-001 | Fleet Production | Cap × (60/Cycle) × N × Eff | Earthwork |
| CN-HAUL-002 | Fleet Balance | N = ceil(Truck Cycle / Loader Cycle) | Earthwork |
| CN-CMP-001 | Roller Production | (W×S×L×E)/(P×27) | Earthwork |
| CN-GRD-001 | Grader Production | (W×S×5280)/(P×9) | Earthwork |
| CN-SCR-001 | Scraper Production | Cap×FF×LF×(60/C)×Eff | Earthwork |
| CN-PILE-001 | Pile Driving Rate | Hours / Cycle per pile | Deep Fdn |
| CN-SHAFT-001 | Drilled Shaft Rate | Hours / Cycle per shaft | Deep Fdn |
| CN-MICRO-001 | Micropile Rate | Hours / Cycle per pile | Deep Fdn |
| CN-DW-001 | Dewatering Flow (Darcy) | Q = k × i × A | Dewatering |
| CN-DW-002 | Wellpoint Count | Perimeter / Spacing | Dewatering |
| CN-GI-001 | Wick Drain Time | t = (D²/8C_h)×ln(1/(1-U%))×F | Ground Impr. |
| CN-GI-002 | Stone Column Replacement | a_s = A_col / A_total | Ground Impr. |
| CN-GI-003 | Grouting Volume | Void Vol × (1+Waste) / Take | Ground Impr. |
| CN-CONC-001 | Concrete Pump Output | Area × Strokes × 60 × Eff / 27 | Concrete |
| CN-TUN-001 | TBM Advance Rate | RPM × Pen × 60 × Hr × Util | Tunneling |

## 7.2 Equation Count Summary

| Category | Count | GeoLab-Dependent |
| --- | --- | --- |
| Equipment Rates | 10 | 1 (altitude) |
| Earthwork Production | 9 | All (soil-driven) |
| Deep Foundations | 3 | All (soil/rock-driven) |
| Dewatering | 2 | All (permeability-driven) |
| Ground Improvement | 3 | All (soil property-driven) |
| Concrete Placement | 1 | Partial (foundation conditions) |
| Tunneling | 1 | All (geology-driven) |
| TOTAL | 29 | 25 of 29 (86%) |

Key Insight: 86% of Construction Engineering equations are directly dependent on GeoLab soil/rock data. This is the strongest domain-to-domain linkage in the entire ENGR-KB system and validates the decision to make GeoLab the foundational data source.

## 7.3 Reference Data Tables

| Data Table | Records | Source | Update |
| --- | --- | --- | --- |
| Equipment Specifications | ~200 models | Manufacturer published | As released |
| Equipment Hourly Rates | ~200 models | USACE EP 1110-1-8 method | Annual recalc |
| Fill Factors by Soil Type | ~12 USCS classes | Caterpillar PHB | Static |
| Compactor Selection Matrix | ~8 soil types | Caterpillar/published | Static |
| Dozer Production Tables | ~6 push distances × 3 sizes | Caterpillar PHB | Static |
| Haul Speed Tables | ~8 surface/grade combos | Published references | Static |
| Pile Driving Rates | ~5 types × 3 difficulties | FHWA/published | User calibration |
| Drilled Shaft Rates | ~5 diameters × 3 ground types | Published references | User calibration |
| Dewatering Method Selection | ~7 methods | Groundwater references | Static |
| Ground Improvement Methods | ~8 methods | FHWA/published | Static |
| Concrete Placement Rates | ~8 methods | ACI/manufacturer | Static |
| TBM Advance Rates | ~5 ground conditions | Published case data | User calibration |
| Site Adjustment Factors | ~8 factor categories | Published/practice | Static |
| Altitude Derating Table | ~6 altitude bands | Engine manufacturer | Static |